## dim_vendor
vendor_id | vendor_name | vendor_category | vendor_rating
V001 | Shree Cements Pvt Ltd | Cement | 3.2
V002 | Bharat MEP Systems Pvt Ltd | MEP | 3.3
V003 | Apex Ready Mix Pvt Ltd | RMC | 4
V004 | Navdurga Infra Services Pvt Ltd | Subcontractor | 3.3
V005 | Suryodaya Earthmovers Pvt Ltd | Equipment Hire | 3.4
V006 | Pragati Logistics Pvt Ltd | Logistics | 4.5
V007 | Omkar Safety Supplies Pvt Ltd | Safety | 3.4
V008 | Vardhman Steel Traders Pvt Ltd | Steel | 3.2
V009 | Triveni Formwork Solutions Pvt Ltd | Formwork | 3.1
V010 | Deccan Electricals Pvt Ltd | Electrical | 4.1
V011 | Eastern Cements Pvt Ltd | Cement | 3.6
V012 | Western MEP Systems Pvt Ltd | MEP | 2.8
V013 | Metro Ready Mix Pvt Ltd | RMC | 4.5
V014 | Reliable Infra Services Pvt Ltd | Subcontractor | 4.2
V015 | Prime Earthmovers Pvt Ltd | Equipment Hire | 3.1
V016 | Shree Logistics Pvt Ltd | Logistics | 4.4
V017 | Bharat Safety Supplies Pvt Ltd | Safety | 3.4
V018 | Apex Steel Traders Pvt Ltd | Steel | 3.7
V019 | Navdurga Formwork Solutions Pvt Ltd | Formwork | 4.7
V020 | Suryodaya Electricals Pvt Ltd | Electrical | 4.8
V021 | Pragati Cements Pvt Ltd | Cement | 4
V022 | Omkar MEP Systems Pvt Ltd | MEP | 4.8
V023 | Vardhman Ready Mix Pvt Ltd | RMC | 3.7
V024 | Triveni Infra Services Pvt Ltd | Subcontractor | 3.5
V025 | Deccan Earthmovers Pvt Ltd | Equipment Hire | 3.1
V026 | Eastern Logistics Pvt Ltd | Logistics | 4.2
V027 | Western Safety Supplies Pvt Ltd | Safety | 3
V028 | Metro Steel Traders Pvt Ltd | Steel | 4.2
V029 | Reliable Formwork Solutions Pvt Ltd | Formwork | 3.8
V030 | Prime Electricals Pvt Ltd | Electrical | 4.3
V031 | Shree Cements Pvt Ltd | Cement | 4
V032 | Bharat MEP Systems Pvt Ltd | MEP | 3.6
V033 | Apex Ready Mix Pvt Ltd | RMC | 3.2
V034 | Navdurga Infra Services Pvt Ltd | Subcontractor | 2.9
V035 | Suryodaya Earthmovers Pvt Ltd | Equipment Hire | 4.3
V036 | Pragati Logistics Pvt Ltd | Logistics | 3.3
V037 | Omkar Safety Supplies Pvt Ltd | Safety | 4.3
V038 | Vardhman Steel Traders Pvt Ltd | Steel | 4.3
V039 | Triveni Formwork Solutions Pvt Ltd | Formwork | 4.3
V040 | Deccan Electricals Pvt Ltd | Electrical | 3
V041 | Eastern Cements Pvt Ltd | Cement | 3.5
V042 | Western MEP Systems Pvt Ltd | MEP | 4.5
V043 | Metro Ready Mix Pvt Ltd | RMC | 3.1
V044 | Reliable Infra Services Pvt Ltd | Subcontractor | 4.8
V045 | Prime Earthmovers Pvt Ltd | Equipment Hire | 3
V046 | Shree Logistics Pvt Ltd | Logistics | 3.6
V047 | Bharat Safety Supplies Pvt Ltd | Safety | 3.3
V048 | Apex Steel Traders Pvt Ltd | Steel | 4.4
V049 | Navdurga Formwork Solutions Pvt Ltd | Formwork | 3.1
V050 | Suryodaya Electricals Pvt Ltd | Electrical | 3.6
V051 | Pragati Cements Pvt Ltd | Cement | 3.9
V052 | Omkar MEP Systems Pvt Ltd | MEP | 4.4
V053 | Vardhman Ready Mix Pvt Ltd | RMC | 3.8
V054 | Triveni Infra Services Pvt Ltd | Subcontractor | 3.1
V055 | Deccan Earthmovers Pvt Ltd | Equipment Hire | 4.5
V056 | Eastern Logistics Pvt Ltd | Logistics | 4.8
V057 | Western Safety Supplies Pvt Ltd | Safety | 3.9
V058 | Metro Steel Traders Pvt Ltd | Steel | 4.4
V059 | Reliable Formwork Solutions Pvt Ltd | Formwork | 4.1
V060 | Prime Electricals Pvt Ltd | Electrical | 4.9

## fact_purchase_order
po_id | project_id | vendor_id | item_description | order_date | promised_date | actual_delivery_date | po_value
PO000001 | PRJ001 | V003 | TMT rebar Fe500D | 2025-11-29 | 2025-12-13 | 2026-01-14 | 35000000
PO000002 | PRJ002 | V012 | OPC 53 grade cement | 2025-09-09 | 2025-09-24 | 2025-09-23 | 2700000
PO000003 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-07-19 | 2025-08-22 | 2025-08-20 | 16200000
PO000004 | PRJ004 | V034 | Structural steel sections | 2026-03-21 | 2026-04-24 | 2026-05-02 | 28100000
PO000005 | PRJ005 | V045 | Aluminium formwork | 2024-10-05 | 2024-11-05 | 2024-11-07 | 9800000
PO000006 | PRJ006 | V056 | Fire-fighting piping | 2025-11-29 | 2025-12-25 | 2025-12-28 | 22100000
PO000007 | PRJ007 | V007 | Electrical cable trays | 2026-01-24 | 2026-02-08 | 2026-02-09 | 17000000
PO000008 | PRJ008 | V018 | Safety harnesses | 2026-05-15 | 2026-06-22 | 2026-06-21 | 18700000
PO000009 | PRJ009 | V029 | Diesel generator hire | 2025-11-08 | 2025-12-13 | 2025-12-13 | 9700000
PO000010 | PRJ010 | V040 | Tower crane hire | 2026-03-08 | 2026-04-22 | 2026-04-19 | 600000
PO000011 | PRJ011 | V007 | Facade glazing panels | 2025-05-18 | 2025-06-11 | 2025-07-05 | 12200000
PO000012 | PRJ012 | V002 | Waterproofing membrane | 2025-03-26 | 2025-04-14 | 2025-04-12 | 25500000
PO000013 | PRJ013 | V013 | TMT rebar Fe500D | 2026-07-06 | 2026-07-31 | 2026-08-04 | 15100000
PO000014 | PRJ014 | V024 | OPC 53 grade cement | 2025-12-10 | 2026-01-20 | 2026-01-23 | 35000000
PO000015 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-01-24 | 2025-03-08 | 2025-03-14 | 1200000
PO000016 | PRJ016 | V046 | Structural steel sections | 2026-03-12 | 2026-04-01 | 2026-04-02 | 19200000
PO000017 | PRJ017 | V057 | Aluminium formwork | 2025-02-06 | 2025-03-14 | 2025-03-18 | 37000000
PO000018 | PRJ018 | V008 | Fire-fighting piping | 2024-11-26 | 2025-01-06 | 2025-01-14 | 17100000
PO000019 | PRJ019 | V019 | Electrical cable trays | 2025-06-13 | 2025-07-08 | 2025-07-06 | 9300000
PO000020 | PRJ020 | V030 | Safety harnesses | 2024-11-12 | 2024-11-27 | 2024-12-05 | 3600000
PO000021 | PRJ021 | V012 | Diesel generator hire | 2024-10-09 | 2024-11-12 | 2024-12-10 | 17800000
PO000022 | PRJ022 | V052 | Tower crane hire | 2024-10-16 | 2024-10-27 | 2024-10-26 | 28100000
PO000023 | PRJ023 | V003 | Facade glazing panels | 2025-03-19 | 2025-04-23 | 2025-04-29 | 15700000
PO000024 | PRJ024 | V014 | Waterproofing membrane | 2026-02-03 | 2026-02-13 | 2026-02-17 | 17600000
PO000025 | PRJ025 | V025 | TMT rebar Fe500D | 2025-02-04 | 2025-03-18 | 2025-03-26 | 17800000
PO000026 | PRJ026 | V036 | OPC 53 grade cement | 2025-12-23 | 2026-01-29 | 2026-01-29 | 29200000
PO000027 | PRJ027 | V047 | Ready-mix concrete M35 | 2026-06-18 | 2026-07-05 | 2026-07-01 | 20700000
PO000028 | PRJ028 | V058 | Structural steel sections | 2026-05-26 | 2026-06-07 | 2026-06-04 | 34900000
PO000029 | PRJ029 | V009 | Aluminium formwork | 2026-07-05 | 2026-07-23 | 2026-07-20 | 14000000
PO000030 | PRJ030 | V020 | Fire-fighting piping | 2025-06-02 | 2025-06-28 | 2025-07-02 | 33400000
PO000031 | PRJ001 | V018 | Electrical cable trays | 2025-07-03 | 2025-07-16 | 2025-08-28 | 26100000
PO000032 | PRJ002 | V042 | Safety harnesses | 2025-01-21 | 2025-02-19 | 2025-02-20 | 8000000
PO000033 | PRJ003 | V053 | Diesel generator hire | 2025-11-24 | 2025-12-05 | 2025-12-07 | 11500000
PO000034 | PRJ004 | V004 | Tower crane hire | 2024-11-09 | 2024-11-25 | 2024-11-25 | 33500000
PO000035 | PRJ005 | V015 | Facade glazing panels | 2025-05-23 | 2025-06-02 | 2025-06-02 | 15200000
PO000036 | PRJ006 | V026 | Waterproofing membrane | 2026-06-11 | 2026-07-06 | 2026-07-05 | 31700000
PO000037 | PRJ007 | V037 | TMT rebar Fe500D | 2025-08-06 | 2025-08-17 | 2025-08-16 | 22300000
PO000038 | PRJ008 | V048 | OPC 53 grade cement | 2026-06-23 | 2026-07-11 | 2026-07-13 | 19900000
PO000039 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-03-26 | 2025-05-09 | 2025-05-07 | 16100000
PO000040 | PRJ010 | V010 | Structural steel sections | 2026-05-24 | 2026-06-29 | 2026-07-04 | 35200000
PO000041 | PRJ011 | V025 | Aluminium formwork | 2025-04-15 | 2025-05-20 | 2025-07-13 | 34500000
PO000042 | PRJ012 | V032 | Fire-fighting piping | 2025-12-11 | 2025-12-25 | 2025-12-30 | 18900000
PO000043 | PRJ013 | V043 | Electrical cable trays | 2025-04-26 | 2025-05-12 | 2025-05-19 | 31500000
PO000044 | PRJ014 | V054 | Safety harnesses | 2025-04-13 | 2025-05-01 | 2025-05-03 | 30200000
PO000045 | PRJ015 | V005 | Diesel generator hire | 2025-05-06 | 2025-05-20 | 2025-05-17 | 32600000
PO000046 | PRJ016 | V016 | Tower crane hire | 2025-03-27 | 2025-04-08 | 2025-04-07 | 6000000
PO000047 | PRJ017 | V027 | Facade glazing panels | 2026-05-01 | 2026-05-11 | 2026-05-11 | 4800000
PO000048 | PRJ018 | V038 | Waterproofing membrane | 2024-12-22 | 2025-01-25 | 2025-01-24 | 11800000
PO000049 | PRJ019 | V049 | TMT rebar Fe500D | 2026-04-26 | 2026-05-18 | 2026-05-26 | 28300000
PO000050 | PRJ020 | V060 | OPC 53 grade cement | 2025-04-13 | 2025-04-26 | 2025-05-02 | 32100000
PO000051 | PRJ021 | V003 | Ready-mix concrete M35 | 2025-06-06 | 2025-06-22 | 2025-07-11 | 20800000
PO000052 | PRJ022 | V022 | Structural steel sections | 2025-06-15 | 2025-07-25 | 2025-07-23 | 13400000
PO000053 | PRJ023 | V033 | Aluminium formwork | 2025-12-10 | 2026-01-16 | 2026-01-15 | 9400000
PO000054 | PRJ024 | V044 | Fire-fighting piping | 2025-08-31 | 2025-09-14 | 2025-09-11 | 13600000
PO000055 | PRJ025 | V055 | Electrical cable trays | 2025-04-09 | 2025-05-10 | 2025-05-09 | 13100000
PO000056 | PRJ026 | V006 | Safety harnesses | 2025-08-11 | 2025-08-25 | 2025-08-23 | 27900000
PO000057 | PRJ027 | V017 | Diesel generator hire | 2026-01-05 | 2026-01-26 | 2026-01-26 | 20900000
PO000058 | PRJ028 | V028 | Tower crane hire | 2026-04-15 | 2026-04-28 | 2026-05-01 | 16600000
PO000059 | PRJ029 | V039 | Facade glazing panels | 2025-08-30 | 2025-09-30 | 2025-10-03 | 34400000
PO000060 | PRJ030 | V050 | Waterproofing membrane | 2025-03-19 | 2025-04-16 | 2025-04-17 | 15900000
PO000061 | PRJ001 | V007 | TMT rebar Fe500D | 2026-05-19 | 2026-06-15 | 2026-07-20 | 35600000
PO000062 | PRJ002 | V012 | OPC 53 grade cement | 2025-09-14 | 2025-10-10 | 2025-10-07 | 10200000
PO000063 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-05-19 | 2025-06-04 | 2025-06-03 | 22800000
PO000064 | PRJ004 | V034 | Structural steel sections | 2025-02-22 | 2025-03-22 | 2025-03-19 | 22400000
PO000065 | PRJ005 | V045 | Aluminium formwork | 2026-04-17 | 2026-05-14 | 2026-05-21 | 7100000
PO000066 | PRJ006 | V056 | Fire-fighting piping | 2026-02-19 | 2026-03-20 | 2026-03-26 | 14700000
PO000067 | PRJ007 | V007 | Electrical cable trays | 2026-04-03 | 2026-05-05 | 2026-05-11 | 10800000
PO000068 | PRJ008 | V018 | Safety harnesses | 2026-01-14 | 2026-02-22 | 2026-02-18 | 33700000
PO000069 | PRJ009 | V029 | Diesel generator hire | 2026-01-20 | 2026-02-24 | 2026-02-28 | 1700000
PO000070 | PRJ010 | V040 | Tower crane hire | 2026-06-30 | 2026-07-18 | 2026-07-23 | 15900000
PO000071 | PRJ011 | V012 | Facade glazing panels | 2025-01-26 | 2025-03-01 | 2025-04-08 | 22100000
PO000072 | PRJ012 | V002 | Waterproofing membrane | 2025-01-02 | 2025-02-07 | 2025-02-13 | 16500000
PO000073 | PRJ013 | V013 | TMT rebar Fe500D | 2025-09-12 | 2025-10-24 | 2025-10-28 | 6100000
PO000074 | PRJ014 | V024 | OPC 53 grade cement | 2025-09-11 | 2025-09-29 | 2025-10-06 | 36900000
PO000075 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-02-18 | 2025-03-06 | 2025-03-04 | 12700000
PO000076 | PRJ016 | V046 | Structural steel sections | 2025-10-02 | 2025-10-17 | 2025-10-14 | 25700000
PO000077 | PRJ017 | V057 | Aluminium formwork | 2025-02-06 | 2025-02-25 | 2025-03-04 | 6800000
PO000078 | PRJ018 | V008 | Fire-fighting piping | 2024-10-12 | 2024-11-16 | 2024-11-23 | 19600000
PO000079 | PRJ019 | V019 | Electrical cable trays | 2026-06-04 | 2026-06-20 | 2026-06-16 | 3200000
PO000080 | PRJ020 | V030 | Safety harnesses | 2025-08-17 | 2025-09-24 | 2025-10-02 | 22000000
PO000081 | PRJ021 | V018 | Diesel generator hire | 2025-03-08 | 2025-03-27 | 2025-05-17 | 25600000
PO000082 | PRJ022 | V052 | Tower crane hire | 2025-10-22 | 2025-11-23 | 2025-11-25 | 18000000
PO000083 | PRJ023 | V003 | Facade glazing panels | 2025-12-25 | 2026-02-01 | 2026-02-05 | 31800000
PO000084 | PRJ024 | V014 | Waterproofing membrane | 2025-03-10 | 2025-04-09 | 2025-04-15 | 18000000
PO000085 | PRJ025 | V025 | TMT rebar Fe500D | 2024-12-12 | 2024-12-25 | 2024-12-29 | 18200000
PO000086 | PRJ026 | V036 | OPC 53 grade cement | 2025-02-13 | 2025-03-12 | 2025-03-14 | 5200000
PO000087 | PRJ027 | V047 | Ready-mix concrete M35 | 2026-02-10 | 2026-03-12 | 2026-03-20 | 8100000
PO000088 | PRJ028 | V058 | Structural steel sections | 2026-04-02 | 2026-05-06 | 2026-05-11 | 25600000
PO000089 | PRJ029 | V009 | Aluminium formwork | 2025-04-15 | 2025-05-08 | 2025-05-14 | 25800000
PO000090 | PRJ030 | V020 | Fire-fighting piping | 2025-09-24 | 2025-10-05 | 2025-10-06 | 14800000
PO000091 | PRJ001 | V025 | Electrical cable trays | 2026-03-07 | 2026-04-02 | 2026-05-16 | 16300000
PO000092 | PRJ002 | V042 | Safety harnesses | 2025-08-17 | 2025-09-03 | 2025-09-10 | 32900000
PO000093 | PRJ003 | V053 | Diesel generator hire | 2025-06-17 | 2025-07-29 | 2025-08-02 | 30300000
PO000094 | PRJ004 | V004 | Tower crane hire | 2026-03-30 | 2026-04-29 | 2026-04-28 | 33800000
PO000095 | PRJ005 | V015 | Facade glazing panels | 2025-11-22 | 2025-12-09 | 2025-12-15 | 5000000
PO000096 | PRJ006 | V026 | Waterproofing membrane | 2025-01-03 | 2025-02-14 | 2025-02-17 | 4800000
PO000097 | PRJ007 | V037 | TMT rebar Fe500D | 2025-06-19 | 2025-07-04 | 2025-07-09 | 15300000
PO000098 | PRJ008 | V048 | OPC 53 grade cement | 2024-10-09 | 2024-11-17 | 2024-11-22 | 14400000
PO000099 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-10-15 | 2025-11-23 | 2025-11-21 | 7000000
PO000100 | PRJ010 | V010 | Structural steel sections | 2025-09-18 | 2025-10-23 | 2025-10-31 | 31400000
PO000101 | PRJ011 | V003 | Aluminium formwork | 2025-06-04 | 2025-07-19 | 2025-08-09 | 33000000
PO000102 | PRJ012 | V032 | Fire-fighting piping | 2025-05-28 | 2025-07-10 | 2025-07-14 | 11400000
PO000103 | PRJ013 | V043 | Electrical cable trays | 2026-05-01 | 2026-06-08 | 2026-06-08 | 13900000
PO000104 | PRJ014 | V054 | Safety harnesses | 2025-06-11 | 2025-06-23 | 2025-06-25 | 8800000
PO000105 | PRJ015 | V005 | Diesel generator hire | 2025-07-30 | 2025-08-11 | 2025-08-08 | 2500000
PO000106 | PRJ016 | V016 | Tower crane hire | 2025-07-13 | 2025-08-24 | 2025-08-31 | 33300000
PO000107 | PRJ017 | V027 | Facade glazing panels | 2024-12-17 | 2025-01-25 | 2025-01-26 | 26100000
PO000108 | PRJ018 | V038 | Waterproofing membrane | 2025-02-26 | 2025-03-30 | 2025-04-02 | 19500000
PO000109 | PRJ019 | V049 | TMT rebar Fe500D | 2026-03-24 | 2026-04-29 | 2026-05-01 | 8300000
PO000110 | PRJ020 | V060 | OPC 53 grade cement | 2025-01-23 | 2025-02-06 | 2025-02-05 | 27800000
PO000111 | PRJ021 | V007 | Ready-mix concrete M35 | 2025-03-19 | 2025-04-24 | 2025-05-29 | 18400000
PO000112 | PRJ022 | V022 | Structural steel sections | 2026-03-20 | 2026-05-03 | 2026-05-07 | 23000000
PO000113 | PRJ023 | V033 | Aluminium formwork | 2026-07-07 | 2026-08-02 | 2026-08-06 | 1300000
PO000114 | PRJ024 | V044 | Fire-fighting piping | 2026-03-31 | 2026-04-22 | 2026-04-26 | 7100000
PO000115 | PRJ025 | V055 | Electrical cable trays | 2025-02-24 | 2025-03-29 | 2025-03-27 | 8200000
PO000116 | PRJ026 | V006 | Safety harnesses | 2025-01-03 | 2025-01-30 | 2025-02-01 | 18000000
PO000117 | PRJ027 | V017 | Diesel generator hire | 2025-01-05 | 2025-01-21 | 2025-01-26 | 14400000
PO000118 | PRJ028 | V028 | Tower crane hire | 2024-10-18 | 2024-11-04 | 2024-11-01 | 26900000
PO000119 | PRJ029 | V039 | Facade glazing panels | 2025-03-05 | 2025-03-18 | 2025-03-27 | 37000000
PO000120 | PRJ030 | V050 | Waterproofing membrane | 2025-04-20 | 2025-05-29 | 2025-06-03 | 12000000
PO000121 | PRJ001 | V012 | TMT rebar Fe500D | 2026-03-01 | 2026-03-22 | 2026-05-11 | 30200000
PO000122 | PRJ002 | V012 | OPC 53 grade cement | 2024-11-16 | 2024-12-30 | 2025-01-06 | 32100000
PO000123 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-08-21 | 2025-09-10 | 2025-09-10 | 16600000
PO000124 | PRJ004 | V034 | Structural steel sections | 2025-06-29 | 2025-07-15 | 2025-07-17 | 27100000
PO000125 | PRJ005 | V045 | Aluminium formwork | 2025-08-08 | 2025-08-21 | 2025-08-26 | 32800000
PO000126 | PRJ006 | V056 | Fire-fighting piping | 2026-04-22 | 2026-05-17 | 2026-05-25 | 28100000
PO000127 | PRJ007 | V007 | Electrical cable trays | 2025-09-20 | 2025-10-28 | 2025-11-05 | 24400000
PO000128 | PRJ008 | V018 | Safety harnesses | 2025-03-02 | 2025-03-28 | 2025-03-27 | 25400000
PO000129 | PRJ009 | V029 | Diesel generator hire | 2026-03-05 | 2026-04-19 | 2026-04-15 | 5600000
PO000130 | PRJ010 | V040 | Tower crane hire | 2026-06-14 | 2026-07-11 | 2026-07-18 | 2600000
PO000131 | PRJ011 | V018 | Facade glazing panels | 2025-01-12 | 2025-02-17 | 2025-04-04 | 25500000
PO000132 | PRJ012 | V002 | Waterproofing membrane | 2026-04-15 | 2026-05-25 | 2026-05-28 | 7200000
PO000133 | PRJ013 | V013 | TMT rebar Fe500D | 2025-05-04 | 2025-05-27 | 2025-05-24 | 4400000
PO000134 | PRJ014 | V024 | OPC 53 grade cement | 2025-10-26 | 2025-11-28 | 2025-11-28 | 6300000
PO000135 | PRJ015 | V035 | Ready-mix concrete M35 | 2026-02-06 | 2026-03-06 | 2026-03-02 | 19900000
PO000136 | PRJ016 | V046 | Structural steel sections | 2025-06-01 | 2025-06-20 | 2025-06-20 | 9800000
PO000137 | PRJ017 | V057 | Aluminium formwork | 2025-01-15 | 2025-02-27 | 2025-03-08 | 4400000
PO000138 | PRJ018 | V008 | Fire-fighting piping | 2026-01-04 | 2026-02-08 | 2026-02-11 | 7600000
PO000139 | PRJ019 | V019 | Electrical cable trays | 2025-03-15 | 2025-04-21 | 2025-04-18 | 29800000
PO000140 | PRJ020 | V030 | Safety harnesses | 2025-03-13 | 2025-04-26 | 2025-04-26 | 24800000
PO000141 | PRJ021 | V025 | Diesel generator hire | 2024-11-17 | 2024-12-07 | 2025-01-01 | 30100000
PO000142 | PRJ022 | V052 | Tower crane hire | 2026-03-08 | 2026-04-02 | 2026-04-05 | 27700000
PO000143 | PRJ023 | V003 | Facade glazing panels | 2025-01-30 | 2025-02-24 | 2025-02-27 | 15300000
PO000144 | PRJ024 | V014 | Waterproofing membrane | 2024-11-19 | 2024-12-14 | 2024-12-15 | 13700000
PO000145 | PRJ025 | V025 | TMT rebar Fe500D | 2025-12-13 | 2026-01-26 | 2026-01-28 | 3600000
PO000146 | PRJ026 | V036 | OPC 53 grade cement | 2024-12-09 | 2024-12-30 | 2025-01-05 | 6900000
PO000147 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-03-15 | 2025-04-12 | 2025-04-09 | 8100000
PO000148 | PRJ028 | V058 | Structural steel sections | 2025-09-28 | 2025-10-31 | 2025-10-27 | 9100000
PO000149 | PRJ029 | V009 | Aluminium formwork | 2025-05-12 | 2025-06-05 | 2025-06-11 | 9900000
PO000150 | PRJ030 | V020 | Fire-fighting piping | 2026-01-02 | 2026-01-24 | 2026-01-30 | 29000000
PO000151 | PRJ001 | V003 | Electrical cable trays | 2025-02-04 | 2025-02-14 | 2025-04-01 | 35300000
PO000152 | PRJ002 | V042 | Safety harnesses | 2025-06-16 | 2025-07-15 | 2025-07-11 | 14000000
PO000153 | PRJ003 | V053 | Diesel generator hire | 2026-07-09 | 2026-08-04 | 2026-08-03 | 15100000
PO000154 | PRJ004 | V004 | Tower crane hire | 2025-03-22 | 2025-04-27 | 2025-04-26 | 29900000
PO000155 | PRJ005 | V015 | Facade glazing panels | 2024-11-25 | 2024-12-30 | 2025-01-07 | 27400000
PO000156 | PRJ006 | V026 | Waterproofing membrane | 2025-05-31 | 2025-07-07 | 2025-07-08 | 3700000
PO000157 | PRJ007 | V037 | TMT rebar Fe500D | 2026-05-03 | 2026-05-31 | 2026-06-03 | 23200000
PO000158 | PRJ008 | V048 | OPC 53 grade cement | 2025-10-27 | 2025-11-20 | 2025-11-29 | 18300000
PO000159 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-01-25 | 2025-03-07 | 2025-03-14 | 900000
PO000160 | PRJ010 | V010 | Structural steel sections | 2026-06-13 | 2026-07-24 | 2026-07-22 | 31400000
PO000161 | PRJ011 | V007 | Aluminium formwork | 2025-08-19 | 2025-09-09 | 2025-10-14 | 5100000
PO000162 | PRJ012 | V032 | Fire-fighting piping | 2024-12-05 | 2025-01-16 | 2025-01-22 | 28100000
PO000163 | PRJ013 | V043 | Electrical cable trays | 2026-03-16 | 2026-04-19 | 2026-04-22 | 33500000
PO000164 | PRJ014 | V054 | Safety harnesses | 2025-12-30 | 2026-01-27 | 2026-01-28 | 200000
PO000165 | PRJ015 | V005 | Diesel generator hire | 2025-10-07 | 2025-10-22 | 2025-10-31 | 6100000
PO000166 | PRJ016 | V016 | Tower crane hire | 2026-02-08 | 2026-03-19 | 2026-03-19 | 16900000
PO000167 | PRJ017 | V027 | Facade glazing panels | 2025-01-20 | 2025-02-15 | 2025-02-13 | 27000000
PO000168 | PRJ018 | V038 | Waterproofing membrane | 2025-01-24 | 2025-03-02 | 2025-03-10 | 3700000
PO000169 | PRJ019 | V049 | TMT rebar Fe500D | 2025-01-25 | 2025-02-14 | 2025-02-13 | 23700000
PO000170 | PRJ020 | V060 | OPC 53 grade cement | 2025-02-28 | 2025-04-13 | 2025-04-09 | 19000000
PO000171 | PRJ021 | V012 | Ready-mix concrete M35 | 2025-01-31 | 2025-02-24 | 2025-04-10 | 20500000
PO000172 | PRJ022 | V022 | Structural steel sections | 2025-12-01 | 2026-01-10 | 2026-01-15 | 34500000
PO000173 | PRJ023 | V033 | Aluminium formwork | 2026-03-06 | 2026-03-19 | 2026-03-28 | 10800000
PO000174 | PRJ024 | V044 | Fire-fighting piping | 2026-05-05 | 2026-06-11 | 2026-06-18 | 25300000
PO000175 | PRJ025 | V055 | Electrical cable trays | 2025-02-27 | 2025-04-05 | 2025-04-12 | 20600000
PO000176 | PRJ026 | V006 | Safety harnesses | 2026-02-05 | 2026-03-01 | 2026-03-10 | 14300000
PO000177 | PRJ027 | V017 | Diesel generator hire | 2025-03-16 | 2025-04-18 | 2025-04-27 | 4400000
PO000178 | PRJ028 | V028 | Tower crane hire | 2025-11-09 | 2025-11-25 | 2025-11-25 | 23900000
PO000179 | PRJ029 | V039 | Facade glazing panels | 2026-02-15 | 2026-03-09 | 2026-03-16 | 7600000
PO000180 | PRJ030 | V050 | Waterproofing membrane | 2025-11-20 | 2025-12-06 | 2025-12-14 | 20200000
PO000181 | PRJ001 | V018 | TMT rebar Fe500D | 2024-10-04 | 2024-11-04 | 2024-11-22 | 6100000
PO000182 | PRJ002 | V012 | OPC 53 grade cement | 2026-07-09 | 2026-07-28 | 2026-07-24 | 14700000
PO000183 | PRJ003 | V023 | Ready-mix concrete M35 | 2026-05-09 | 2026-06-17 | 2026-06-14 | 22600000
PO000184 | PRJ004 | V034 | Structural steel sections | 2026-01-19 | 2026-01-30 | 2026-01-27 | 600000
PO000185 | PRJ005 | V045 | Aluminium formwork | 2025-06-27 | 2025-07-26 | 2025-08-02 | 2000000
PO000186 | PRJ006 | V056 | Fire-fighting piping | 2025-06-20 | 2025-07-27 | 2025-07-25 | 20700000
PO000187 | PRJ007 | V007 | Electrical cable trays | 2025-03-19 | 2025-04-16 | 2025-04-16 | 23900000
PO000188 | PRJ008 | V018 | Safety harnesses | 2025-05-30 | 2025-06-29 | 2025-07-07 | 13900000
PO000189 | PRJ009 | V029 | Diesel generator hire | 2024-12-04 | 2024-12-21 | 2024-12-30 | 22000000
PO000190 | PRJ010 | V040 | Tower crane hire | 2026-07-03 | 2026-07-19 | 2026-07-16 | 22600000
PO000191 | PRJ011 | V025 | Facade glazing panels | 2026-03-23 | 2026-04-10 | 2026-05-03 | 11800000
PO000192 | PRJ012 | V002 | Waterproofing membrane | 2025-09-15 | 2025-10-01 | 2025-10-04 | 10400000
PO000193 | PRJ013 | V013 | TMT rebar Fe500D | 2025-06-01 | 2025-07-08 | 2025-07-06 | 15600000
PO000194 | PRJ014 | V024 | OPC 53 grade cement | 2026-05-15 | 2026-06-09 | 2026-06-13 | 300000
PO000195 | PRJ015 | V035 | Ready-mix concrete M35 | 2026-05-10 | 2026-05-29 | 2026-05-27 | 33100000
PO000196 | PRJ016 | V046 | Structural steel sections | 2026-01-27 | 2026-02-15 | 2026-02-18 | 33900000
PO000197 | PRJ017 | V057 | Aluminium formwork | 2025-06-23 | 2025-07-22 | 2025-07-22 | 20600000
PO000198 | PRJ018 | V008 | Fire-fighting piping | 2025-08-23 | 2025-09-25 | 2025-09-30 | 400000
PO000199 | PRJ019 | V019 | Electrical cable trays | 2025-02-15 | 2025-03-21 | 2025-03-21 | 29700000
PO000200 | PRJ020 | V030 | Safety harnesses | 2025-12-17 | 2026-01-26 | 2026-01-31 | 10900000
PO000201 | PRJ021 | V003 | Diesel generator hire | 2025-02-18 | 2025-03-27 | 2025-04-24 | 12900000
PO000202 | PRJ022 | V052 | Tower crane hire | 2025-05-23 | 2025-06-11 | 2025-06-13 | 32300000
PO000203 | PRJ023 | V003 | Facade glazing panels | 2025-10-02 | 2025-10-31 | 2025-11-05 | 28400000
PO000204 | PRJ024 | V014 | Waterproofing membrane | 2026-06-21 | 2026-07-09 | 2026-07-18 | 23100000
PO000205 | PRJ025 | V025 | TMT rebar Fe500D | 2026-02-26 | 2026-03-17 | 2026-03-20 | 37600000
PO000206 | PRJ026 | V036 | OPC 53 grade cement | 2025-06-08 | 2025-07-13 | 2025-07-16 | 29300000
PO000207 | PRJ027 | V047 | Ready-mix concrete M35 | 2024-12-18 | 2025-01-22 | 2025-01-23 | 21000000
PO000208 | PRJ028 | V058 | Structural steel sections | 2025-02-26 | 2025-03-10 | 2025-03-19 | 14200000
PO000209 | PRJ029 | V009 | Aluminium formwork | 2025-06-10 | 2025-07-01 | 2025-07-01 | 32500000
PO000210 | PRJ030 | V020 | Fire-fighting piping | 2025-06-02 | 2025-07-17 | 2025-07-26 | 25400000
PO000211 | PRJ001 | V007 | Electrical cable trays | 2024-12-24 | 2025-01-22 | 2025-03-08 | 25900000
PO000212 | PRJ002 | V042 | Safety harnesses | 2025-12-23 | 2026-01-08 | 2026-01-04 | 23500000
PO000213 | PRJ003 | V053 | Diesel generator hire | 2024-11-07 | 2024-12-18 | 2024-12-14 | 31900000
PO000214 | PRJ004 | V004 | Tower crane hire | 2024-11-29 | 2024-12-15 | 2024-12-15 | 29400000
PO000215 | PRJ005 | V015 | Facade glazing panels | 2026-01-20 | 2026-02-14 | 2026-02-21 | 33400000
PO000216 | PRJ006 | V026 | Waterproofing membrane | 2026-04-09 | 2026-05-12 | 2026-05-14 | 25200000
PO000217 | PRJ007 | V037 | TMT rebar Fe500D | 2024-12-24 | 2025-01-12 | 2025-01-12 | 24000000
PO000218 | PRJ008 | V048 | OPC 53 grade cement | 2025-10-31 | 2025-11-16 | 2025-11-23 | 24400000
PO000219 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-06-25 | 2025-07-06 | 2025-07-11 | 22800000
PO000220 | PRJ010 | V010 | Structural steel sections | 2025-01-30 | 2025-03-08 | 2025-03-04 | 20400000
PO000221 | PRJ011 | V012 | Aluminium formwork | 2026-03-30 | 2026-04-10 | 2026-05-05 | 33500000
PO000222 | PRJ012 | V032 | Fire-fighting piping | 2024-12-31 | 2025-01-11 | 2025-01-16 | 3200000
PO000223 | PRJ013 | V043 | Electrical cable trays | 2024-12-29 | 2025-02-12 | 2025-02-15 | 11600000
PO000224 | PRJ014 | V054 | Safety harnesses | 2024-10-26 | 2024-11-22 | 2024-11-27 | 35400000
PO000225 | PRJ015 | V005 | Diesel generator hire | 2025-11-16 | 2025-12-19 | 2025-12-27 | 26500000
PO000226 | PRJ016 | V016 | Tower crane hire | 2025-03-02 | 2025-04-11 | 2025-04-18 | 19300000
PO000227 | PRJ017 | V027 | Facade glazing panels | 2024-12-26 | 2025-02-05 | 2025-02-04 | 400000
PO000228 | PRJ018 | V038 | Waterproofing membrane | 2025-10-13 | 2025-10-31 | 2025-11-09 | 16700000
PO000229 | PRJ019 | V049 | TMT rebar Fe500D | 2025-02-16 | 2025-03-06 | 2025-03-13 | 5200000
PO000230 | PRJ020 | V060 | OPC 53 grade cement | 2025-05-01 | 2025-05-28 | 2025-05-24 | 1500000
PO000231 | PRJ021 | V018 | Ready-mix concrete M35 | 2024-12-03 | 2025-01-06 | 2025-01-31 | 6200000
PO000232 | PRJ022 | V022 | Structural steel sections | 2025-09-17 | 2025-09-30 | 2025-09-28 | 19500000
PO000233 | PRJ023 | V033 | Aluminium formwork | 2026-05-22 | 2026-06-28 | 2026-06-25 | 23600000
PO000234 | PRJ024 | V044 | Fire-fighting piping | 2026-02-02 | 2026-02-22 | 2026-03-01 | 1600000
PO000235 | PRJ025 | V055 | Electrical cable trays | 2026-03-03 | 2026-03-24 | 2026-04-01 | 9000000
PO000236 | PRJ026 | V006 | Safety harnesses | 2024-10-03 | 2024-10-26 | 2024-10-26 | 36300000
PO000237 | PRJ027 | V017 | Diesel generator hire | 2026-04-08 | 2026-05-19 | 2026-05-25 | 19300000
PO000238 | PRJ028 | V028 | Tower crane hire | 2026-05-07 | 2026-06-15 | 2026-06-17 | 1800000
PO000239 | PRJ029 | V039 | Facade glazing panels | 2025-08-17 | 2025-09-06 | 2025-09-07 | 4900000
PO000240 | PRJ030 | V050 | Waterproofing membrane | 2025-01-06 | 2025-01-30 | 2025-01-31 | 10900000
PO000241 | PRJ001 | V025 | TMT rebar Fe500D | 2026-02-12 | 2026-03-20 | 2026-05-06 | 21700000
PO000242 | PRJ002 | V012 | OPC 53 grade cement | 2025-10-17 | 2025-11-20 | 2025-11-17 | 3000000
PO000243 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-07-04 | 2025-07-20 | 2025-07-29 | 21200000
PO000244 | PRJ004 | V034 | Structural steel sections | 2024-12-28 | 2025-01-22 | 2025-01-21 | 1100000
PO000245 | PRJ005 | V045 | Aluminium formwork | 2025-06-13 | 2025-07-25 | 2025-07-28 | 31500000
PO000246 | PRJ006 | V056 | Fire-fighting piping | 2025-10-19 | 2025-11-17 | 2025-11-16 | 12800000
PO000247 | PRJ007 | V007 | Electrical cable trays | 2025-09-03 | 2025-09-24 | 2025-09-25 | 32000000
PO000248 | PRJ008 | V018 | Safety harnesses | 2025-04-16 | 2025-05-15 | 2025-05-13 | 19400000
PO000249 | PRJ009 | V029 | Diesel generator hire | 2025-01-03 | 2025-02-12 | 2025-02-12 | 17700000
PO000250 | PRJ010 | V040 | Tower crane hire | 2025-01-27 | 2025-03-09 | 2025-03-16 | 19500000
PO000251 | PRJ011 | V003 | Facade glazing panels | 2026-03-23 | 2026-04-04 | 2026-05-14 | 22100000
PO000252 | PRJ012 | V002 | Waterproofing membrane | 2025-01-12 | 2025-02-12 | 2025-02-17 | 13600000
PO000253 | PRJ013 | V013 | TMT rebar Fe500D | 2026-05-22 | 2026-06-14 | 2026-06-10 | 10400000
PO000254 | PRJ014 | V024 | OPC 53 grade cement | 2025-10-03 | 2025-10-16 | 2025-10-24 | 30600000
PO000255 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-01-22 | 2025-02-04 | 2025-02-06 | 30000000
PO000256 | PRJ016 | V046 | Structural steel sections | 2025-07-23 | 2025-08-13 | 2025-08-12 | 24700000
PO000257 | PRJ017 | V057 | Aluminium formwork | 2026-04-25 | 2026-05-10 | 2026-05-18 | 17200000
PO000258 | PRJ018 | V008 | Fire-fighting piping | 2025-07-25 | 2025-08-25 | 2025-08-27 | 12400000
PO000259 | PRJ019 | V019 | Electrical cable trays | 2025-11-08 | 2025-12-19 | 2025-12-21 | 37800000
PO000260 | PRJ020 | V030 | Safety harnesses | 2026-07-08 | 2026-08-05 | 2026-08-11 | 33800000
PO000261 | PRJ021 | V007 | Diesel generator hire | 2026-02-04 | 2026-02-17 | 2026-03-07 | 3500000
PO000262 | PRJ022 | V052 | Tower crane hire | 2025-03-22 | 2025-05-02 | 2025-05-11 | 29100000
PO000263 | PRJ023 | V003 | Facade glazing panels | 2025-02-28 | 2025-04-07 | 2025-04-15 | 6200000
PO000264 | PRJ024 | V014 | Waterproofing membrane | 2025-01-22 | 2025-02-06 | 2025-02-09 | 15600000
PO000265 | PRJ025 | V025 | TMT rebar Fe500D | 2026-02-16 | 2026-02-28 | 2026-02-25 | 2300000
PO000266 | PRJ026 | V036 | OPC 53 grade cement | 2024-10-02 | 2024-10-22 | 2024-10-27 | 28800000
PO000267 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-12-18 | 2026-01-03 | 2026-01-09 | 31900000
PO000268 | PRJ028 | V058 | Structural steel sections | 2025-05-20 | 2025-07-03 | 2025-07-07 | 16000000
PO000269 | PRJ029 | V009 | Aluminium formwork | 2026-01-21 | 2026-02-20 | 2026-03-01 | 25100000
PO000270 | PRJ030 | V020 | Fire-fighting piping | 2025-08-09 | 2025-09-15 | 2025-09-24 | 13000000
PO000271 | PRJ001 | V012 | Electrical cable trays | 2025-09-23 | 2025-11-07 | 2025-12-18 | 7100000
PO000272 | PRJ002 | V042 | Safety harnesses | 2026-02-16 | 2026-04-02 | 2026-04-02 | 18800000
PO000273 | PRJ003 | V053 | Diesel generator hire | 2025-04-20 | 2025-05-19 | 2025-05-26 | 11000000
PO000274 | PRJ004 | V004 | Tower crane hire | 2026-02-22 | 2026-03-19 | 2026-03-18 | 14600000
PO000275 | PRJ005 | V015 | Facade glazing panels | 2026-02-20 | 2026-04-03 | 2026-04-08 | 35000000
PO000276 | PRJ006 | V026 | Waterproofing membrane | 2026-01-09 | 2026-01-19 | 2026-01-27 | 7100000
PO000277 | PRJ007 | V037 | TMT rebar Fe500D | 2026-06-19 | 2026-07-16 | 2026-07-20 | 600000
PO000278 | PRJ008 | V048 | OPC 53 grade cement | 2025-06-05 | 2025-06-30 | 2025-06-26 | 11900000
PO000279 | PRJ009 | V059 | Ready-mix concrete M35 | 2024-12-29 | 2025-01-28 | 2025-01-31 | 35600000
PO000280 | PRJ010 | V010 | Structural steel sections | 2025-07-02 | 2025-08-02 | 2025-08-06 | 35600000
PO000281 | PRJ011 | V018 | Aluminium formwork | 2025-01-10 | 2025-02-21 | 2025-03-16 | 34900000
PO000282 | PRJ012 | V032 | Fire-fighting piping | 2026-05-29 | 2026-06-16 | 2026-06-25 | 18900000
PO000283 | PRJ013 | V043 | Electrical cable trays | 2026-06-25 | 2026-07-05 | 2026-07-06 | 22200000
PO000284 | PRJ014 | V054 | Safety harnesses | 2025-07-11 | 2025-07-25 | 2025-07-31 | 29800000
PO000285 | PRJ015 | V005 | Diesel generator hire | 2025-05-29 | 2025-06-12 | 2025-06-09 | 14500000
PO000286 | PRJ016 | V016 | Tower crane hire | 2026-06-11 | 2026-07-19 | 2026-07-19 | 26700000
PO000287 | PRJ017 | V027 | Facade glazing panels | 2025-04-13 | 2025-05-01 | 2025-04-27 | 10700000
PO000288 | PRJ018 | V038 | Waterproofing membrane | 2025-01-10 | 2025-01-21 | 2025-01-20 | 30100000
PO000289 | PRJ019 | V049 | TMT rebar Fe500D | 2025-01-16 | 2025-02-16 | 2025-02-25 | 37300000
PO000290 | PRJ020 | V060 | OPC 53 grade cement | 2026-06-08 | 2026-07-15 | 2026-07-17 | 13900000
PO000291 | PRJ021 | V025 | Ready-mix concrete M35 | 2026-06-27 | 2026-07-25 | 2026-09-12 | 17300000
PO000292 | PRJ022 | V022 | Structural steel sections | 2025-05-27 | 2025-06-20 | 2025-06-26 | 16400000
PO000293 | PRJ023 | V033 | Aluminium formwork | 2026-06-13 | 2026-07-12 | 2026-07-11 | 7400000
PO000294 | PRJ024 | V044 | Fire-fighting piping | 2025-06-06 | 2025-07-03 | 2025-07-10 | 30300000
PO000295 | PRJ025 | V055 | Electrical cable trays | 2024-12-27 | 2025-02-10 | 2025-02-11 | 18500000
PO000296 | PRJ026 | V006 | Safety harnesses | 2026-06-10 | 2026-07-23 | 2026-07-24 | 16300000
PO000297 | PRJ027 | V017 | Diesel generator hire | 2024-10-11 | 2024-10-30 | 2024-10-27 | 20200000
PO000298 | PRJ028 | V028 | Tower crane hire | 2025-08-06 | 2025-08-17 | 2025-08-13 | 11300000
PO000299 | PRJ029 | V039 | Facade glazing panels | 2024-12-06 | 2025-01-01 | 2025-01-08 | 34100000
PO000300 | PRJ030 | V050 | Waterproofing membrane | 2025-08-06 | 2025-09-18 | 2025-09-21 | 35600000
PO000301 | PRJ001 | V003 | TMT rebar Fe500D | 2024-11-27 | 2024-12-10 | 2025-01-24 | 14400000
PO000302 | PRJ002 | V012 | OPC 53 grade cement | 2025-03-10 | 2025-04-08 | 2025-04-17 | 19300000
PO000303 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-12-27 | 2026-01-29 | 2026-02-07 | 32200000
PO000304 | PRJ004 | V034 | Structural steel sections | 2025-03-17 | 2025-04-18 | 2025-04-23 | 12700000
PO000305 | PRJ005 | V045 | Aluminium formwork | 2025-08-02 | 2025-08-22 | 2025-08-20 | 32300000
PO000306 | PRJ006 | V056 | Fire-fighting piping | 2025-11-28 | 2025-12-20 | 2025-12-29 | 33100000
PO000307 | PRJ007 | V007 | Electrical cable trays | 2025-09-24 | 2025-10-10 | 2025-10-16 | 18900000
PO000308 | PRJ008 | V018 | Safety harnesses | 2026-04-07 | 2026-05-13 | 2026-05-19 | 19900000
PO000309 | PRJ009 | V029 | Diesel generator hire | 2025-03-26 | 2025-04-29 | 2025-05-08 | 700000
PO000310 | PRJ010 | V040 | Tower crane hire | 2025-11-28 | 2025-12-12 | 2025-12-17 | 35100000
PO000311 | PRJ011 | V007 | Facade glazing panels | 2026-03-05 | 2026-03-28 | 2026-05-01 | 36500000
PO000312 | PRJ012 | V002 | Waterproofing membrane | 2025-06-09 | 2025-06-28 | 2025-07-06 | 26100000
PO000313 | PRJ013 | V013 | TMT rebar Fe500D | 2024-12-19 | 2025-01-08 | 2025-01-05 | 10700000
PO000314 | PRJ014 | V024 | OPC 53 grade cement | 2025-06-22 | 2025-07-26 | 2025-07-26 | 4700000
PO000315 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-11-16 | 2025-12-17 | 2025-12-19 | 22600000
PO000316 | PRJ016 | V046 | Structural steel sections | 2026-05-05 | 2026-06-13 | 2026-06-15 | 15300000
PO000317 | PRJ017 | V057 | Aluminium formwork | 2026-05-28 | 2026-06-29 | 2026-07-07 | 11500000
PO000318 | PRJ018 | V008 | Fire-fighting piping | 2026-05-14 | 2026-06-15 | 2026-06-20 | 32500000
PO000319 | PRJ019 | V019 | Electrical cable trays | 2025-08-22 | 2025-09-27 | 2025-09-30 | 21600000
PO000320 | PRJ020 | V030 | Safety harnesses | 2024-12-16 | 2025-01-27 | 2025-01-30 | 26100000
PO000321 | PRJ021 | V012 | Diesel generator hire | 2026-06-21 | 2026-07-24 | 2026-08-16 | 32800000
PO000322 | PRJ022 | V052 | Tower crane hire | 2025-07-10 | 2025-08-11 | 2025-08-20 | 28700000
PO000323 | PRJ023 | V003 | Facade glazing panels | 2025-03-22 | 2025-05-01 | 2025-05-03 | 15200000
PO000324 | PRJ024 | V014 | Waterproofing membrane | 2026-03-09 | 2026-03-29 | 2026-03-30 | 26100000
PO000325 | PRJ025 | V025 | TMT rebar Fe500D | 2025-03-14 | 2025-04-13 | 2025-04-09 | 18300000
PO000326 | PRJ026 | V036 | OPC 53 grade cement | 2026-05-26 | 2026-07-05 | 2026-07-05 | 2200000
PO000327 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-06-10 | 2025-06-22 | 2025-06-20 | 29900000
PO000328 | PRJ028 | V058 | Structural steel sections | 2025-12-22 | 2026-01-17 | 2026-01-16 | 5000000
PO000329 | PRJ029 | V009 | Aluminium formwork | 2025-11-25 | 2026-01-09 | 2026-01-15 | 19500000
PO000330 | PRJ030 | V020 | Fire-fighting piping | 2025-09-29 | 2025-10-10 | 2025-10-10 | 27100000
PO000331 | PRJ001 | V018 | Electrical cable trays | 2025-01-06 | 2025-01-31 | 2025-02-27 | 33800000
PO000332 | PRJ002 | V042 | Safety harnesses | 2025-02-03 | 2025-03-15 | 2025-03-18 | 12500000
PO000333 | PRJ003 | V053 | Diesel generator hire | 2025-02-10 | 2025-02-27 | 2025-03-03 | 28100000
PO000334 | PRJ004 | V004 | Tower crane hire | 2025-05-28 | 2025-06-08 | 2025-06-14 | 15600000
PO000335 | PRJ005 | V015 | Facade glazing panels | 2025-07-30 | 2025-08-11 | 2025-08-07 | 17100000
PO000336 | PRJ006 | V026 | Waterproofing membrane | 2024-10-10 | 2024-10-26 | 2024-10-23 | 35600000
PO000337 | PRJ007 | V037 | TMT rebar Fe500D | 2025-08-18 | 2025-09-13 | 2025-09-14 | 13800000
PO000338 | PRJ008 | V048 | OPC 53 grade cement | 2025-06-26 | 2025-07-08 | 2025-07-04 | 35100000
PO000339 | PRJ009 | V059 | Ready-mix concrete M35 | 2026-04-03 | 2026-05-14 | 2026-05-17 | 3800000
PO000340 | PRJ010 | V010 | Structural steel sections | 2024-11-23 | 2025-01-07 | 2025-01-05 | 8100000
PO000341 | PRJ011 | V025 | Aluminium formwork | 2025-07-21 | 2025-08-31 | 2025-10-20 | 17700000
PO000342 | PRJ012 | V032 | Fire-fighting piping | 2025-01-18 | 2025-02-02 | 2025-02-02 | 19500000
PO000343 | PRJ013 | V043 | Electrical cable trays | 2024-12-20 | 2025-01-28 | 2025-01-26 | 19200000
PO000344 | PRJ014 | V054 | Safety harnesses | 2025-11-29 | 2025-12-25 | 2026-01-02 | 33900000
PO000345 | PRJ015 | V005 | Diesel generator hire | 2026-03-28 | 2026-05-04 | 2026-05-06 | 16200000
PO000346 | PRJ016 | V016 | Tower crane hire | 2026-05-05 | 2026-06-09 | 2026-06-09 | 25600000
PO000347 | PRJ017 | V027 | Facade glazing panels | 2026-04-29 | 2026-05-21 | 2026-05-20 | 4100000
PO000348 | PRJ018 | V038 | Waterproofing membrane | 2025-05-04 | 2025-05-31 | 2025-05-29 | 28500000
PO000349 | PRJ019 | V049 | TMT rebar Fe500D | 2025-11-14 | 2025-12-21 | 2025-12-17 | 5200000
PO000350 | PRJ020 | V060 | OPC 53 grade cement | 2025-10-08 | 2025-11-13 | 2025-11-10 | 800000
PO000351 | PRJ021 | V003 | Ready-mix concrete M35 | 2025-01-28 | 2025-02-08 | 2025-03-19 | 1900000
PO000352 | PRJ022 | V022 | Structural steel sections | 2025-01-17 | 2025-02-01 | 2025-02-08 | 11500000
PO000353 | PRJ023 | V033 | Aluminium formwork | 2025-07-04 | 2025-08-02 | 2025-08-09 | 14900000
PO000354 | PRJ024 | V044 | Fire-fighting piping | 2026-05-13 | 2026-06-16 | 2026-06-17 | 12000000
PO000355 | PRJ025 | V055 | Electrical cable trays | 2026-04-02 | 2026-04-16 | 2026-04-18 | 28200000
PO000356 | PRJ026 | V006 | Safety harnesses | 2024-12-31 | 2025-02-07 | 2025-02-07 | 8000000
PO000357 | PRJ027 | V017 | Diesel generator hire | 2024-10-28 | 2024-12-02 | 2024-12-07 | 14700000
PO000358 | PRJ028 | V028 | Tower crane hire | 2025-04-28 | 2025-06-03 | 2025-06-01 | 22600000
PO000359 | PRJ029 | V039 | Facade glazing panels | 2026-01-05 | 2026-02-09 | 2026-02-05 | 14000000
PO000360 | PRJ030 | V050 | Waterproofing membrane | 2025-04-19 | 2025-05-28 | 2025-05-26 | 11100000
PO000361 | PRJ001 | V007 | TMT rebar Fe500D | 2024-10-11 | 2024-11-05 | 2024-12-30 | 23900000
PO000362 | PRJ002 | V012 | OPC 53 grade cement | 2024-11-26 | 2024-12-07 | 2024-12-04 | 13600000
PO000363 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-07-21 | 2025-09-03 | 2025-09-05 | 8100000
PO000364 | PRJ004 | V034 | Structural steel sections | 2026-04-26 | 2026-05-21 | 2026-05-30 | 11000000
PO000365 | PRJ005 | V045 | Aluminium formwork | 2024-12-02 | 2024-12-12 | 2024-12-20 | 6900000
PO000366 | PRJ006 | V056 | Fire-fighting piping | 2026-01-17 | 2026-01-31 | 2026-02-03 | 32400000
PO000367 | PRJ007 | V007 | Electrical cable trays | 2024-10-21 | 2024-11-09 | 2024-11-08 | 28100000
PO000368 | PRJ008 | V018 | Safety harnesses | 2025-03-04 | 2025-04-09 | 2025-04-06 | 2600000
PO000369 | PRJ009 | V029 | Diesel generator hire | 2024-12-06 | 2025-01-12 | 2025-01-18 | 21500000
PO000370 | PRJ010 | V040 | Tower crane hire | 2026-02-28 | 2026-03-24 | 2026-03-21 | 37100000
PO000371 | PRJ011 | V012 | Facade glazing panels | 2024-12-18 | 2025-01-01 | 2025-02-08 | 2100000
PO000372 | PRJ012 | V002 | Waterproofing membrane | 2026-06-14 | 2026-07-07 | 2026-07-04 | 4600000
PO000373 | PRJ013 | V013 | TMT rebar Fe500D | 2025-10-06 | 2025-11-20 | 2025-11-22 | 19100000
PO000374 | PRJ014 | V024 | OPC 53 grade cement | 2026-05-08 | 2026-05-28 | 2026-05-24 | 27700000
PO000375 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-10-01 | 2025-10-13 | 2025-10-19 | 17000000
PO000376 | PRJ016 | V046 | Structural steel sections | 2026-01-02 | 2026-02-10 | 2026-02-09 | 9400000
PO000377 | PRJ017 | V057 | Aluminium formwork | 2024-12-15 | 2025-01-06 | 2025-01-07 | 23300000
PO000378 | PRJ018 | V008 | Fire-fighting piping | 2026-04-27 | 2026-05-19 | 2026-05-24 | 14500000
PO000379 | PRJ019 | V019 | Electrical cable trays | 2024-10-21 | 2024-11-27 | 2024-11-29 | 8100000
PO000380 | PRJ020 | V030 | Safety harnesses | 2026-07-02 | 2026-07-29 | 2026-07-31 | 9500000
PO000381 | PRJ021 | V018 | Diesel generator hire | 2025-06-28 | 2025-08-11 | 2025-10-03 | 27300000
PO000382 | PRJ022 | V052 | Tower crane hire | 2026-07-02 | 2026-07-28 | 2026-07-27 | 5800000
PO000383 | PRJ023 | V003 | Facade glazing panels | 2025-02-27 | 2025-03-19 | 2025-03-27 | 8100000
PO000384 | PRJ024 | V014 | Waterproofing membrane | 2025-11-06 | 2025-11-19 | 2025-11-24 | 36800000
PO000385 | PRJ025 | V025 | TMT rebar Fe500D | 2025-09-18 | 2025-10-29 | 2025-10-31 | 2600000
PO000386 | PRJ026 | V036 | OPC 53 grade cement | 2025-10-19 | 2025-11-29 | 2025-12-08 | 22300000
PO000387 | PRJ027 | V047 | Ready-mix concrete M35 | 2026-06-29 | 2026-08-09 | 2026-08-07 | 36200000
PO000388 | PRJ028 | V058 | Structural steel sections | 2025-02-21 | 2025-03-04 | 2025-03-08 | 10100000
PO000389 | PRJ029 | V009 | Aluminium formwork | 2025-09-19 | 2025-10-02 | 2025-10-09 | 32700000
PO000390 | PRJ030 | V020 | Fire-fighting piping | 2026-01-15 | 2026-02-14 | 2026-02-16 | 21000000
PO000391 | PRJ001 | V025 | Electrical cable trays | 2025-05-04 | 2025-05-30 | 2025-07-21 | 6700000
PO000392 | PRJ002 | V042 | Safety harnesses | 2025-03-12 | 2025-04-11 | 2025-04-11 | 700000
PO000393 | PRJ003 | V053 | Diesel generator hire | 2025-04-24 | 2025-06-03 | 2025-06-06 | 11200000
PO000394 | PRJ004 | V004 | Tower crane hire | 2025-10-25 | 2025-11-07 | 2025-11-04 | 12700000
PO000395 | PRJ005 | V015 | Facade glazing panels | 2025-06-27 | 2025-08-05 | 2025-08-11 | 37000000
PO000396 | PRJ006 | V026 | Waterproofing membrane | 2025-06-01 | 2025-06-14 | 2025-06-23 | 28500000
PO000397 | PRJ007 | V037 | TMT rebar Fe500D | 2026-03-26 | 2026-04-05 | 2026-04-13 | 25300000
PO000398 | PRJ008 | V048 | OPC 53 grade cement | 2025-03-02 | 2025-03-14 | 2025-03-22 | 4400000
PO000399 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-02-05 | 2025-02-15 | 2025-02-15 | 7300000
PO000400 | PRJ010 | V010 | Structural steel sections | 2025-01-15 | 2025-01-27 | 2025-01-26 | 9500000
PO000401 | PRJ011 | V003 | Aluminium formwork | 2025-05-04 | 2025-05-25 | 2025-06-15 | 28600000
PO000402 | PRJ012 | V032 | Fire-fighting piping | 2025-08-27 | 2025-09-15 | 2025-09-18 | 6900000
PO000403 | PRJ013 | V043 | Electrical cable trays | 2026-06-19 | 2026-07-23 | 2026-07-29 | 18700000
PO000404 | PRJ014 | V054 | Safety harnesses | 2025-06-20 | 2025-07-29 | 2025-07-31 | 20400000
PO000405 | PRJ015 | V005 | Diesel generator hire | 2025-03-20 | 2025-04-30 | 2025-05-08 | 32300000
PO000406 | PRJ016 | V016 | Tower crane hire | 2026-01-09 | 2026-02-19 | 2026-02-15 | 27300000
PO000407 | PRJ017 | V027 | Facade glazing panels | 2025-09-30 | 2025-11-07 | 2025-11-14 | 20000000
PO000408 | PRJ018 | V038 | Waterproofing membrane | 2025-03-08 | 2025-04-10 | 2025-04-10 | 13100000
PO000409 | PRJ019 | V049 | TMT rebar Fe500D | 2025-10-12 | 2025-11-16 | 2025-11-14 | 1200000
PO000410 | PRJ020 | V060 | OPC 53 grade cement | 2025-10-18 | 2025-11-03 | 2025-11-08 | 22600000
PO000411 | PRJ021 | V007 | Ready-mix concrete M35 | 2025-06-17 | 2025-07-31 | 2025-09-20 | 33300000
PO000412 | PRJ022 | V022 | Structural steel sections | 2025-04-05 | 2025-05-08 | 2025-05-09 | 18700000
PO000413 | PRJ023 | V033 | Aluminium formwork | 2025-05-06 | 2025-05-23 | 2025-05-30 | 35200000
PO000414 | PRJ024 | V044 | Fire-fighting piping | 2025-11-22 | 2025-12-11 | 2025-12-08 | 35000000
PO000415 | PRJ025 | V055 | Electrical cable trays | 2025-07-05 | 2025-08-16 | 2025-08-23 | 24000000
PO000416 | PRJ026 | V006 | Safety harnesses | 2026-04-19 | 2026-05-21 | 2026-05-23 | 27600000
PO000417 | PRJ027 | V017 | Diesel generator hire | 2024-10-21 | 2024-11-16 | 2024-11-21 | 24600000
PO000418 | PRJ028 | V028 | Tower crane hire | 2026-05-19 | 2026-06-18 | 2026-06-22 | 28200000
PO000419 | PRJ029 | V039 | Facade glazing panels | 2024-10-19 | 2024-11-20 | 2024-11-16 | 10000000
PO000420 | PRJ030 | V050 | Waterproofing membrane | 2026-02-05 | 2026-02-24 | 2026-02-26 | 4600000
PO000421 | PRJ001 | V012 | TMT rebar Fe500D | 2026-07-14 | 2026-08-19 | 2026-09-12 | 33500000
PO000422 | PRJ002 | V012 | OPC 53 grade cement | 2024-10-07 | 2024-11-17 | 2024-11-26 | 6700000
PO000423 | PRJ003 | V023 | Ready-mix concrete M35 | 2024-10-01 | 2024-11-08 | 2024-11-05 | 23700000
PO000424 | PRJ004 | V034 | Structural steel sections | 2025-04-01 | 2025-04-27 | 2025-04-23 | 13700000
PO000425 | PRJ005 | V045 | Aluminium formwork | 2025-02-18 | 2025-03-09 | 2025-03-13 | 24300000
PO000426 | PRJ006 | V056 | Fire-fighting piping | 2025-11-23 | 2025-12-26 | 2025-12-30 | 35200000
PO000427 | PRJ007 | V007 | Electrical cable trays | 2026-06-23 | 2026-07-24 | 2026-07-27 | 18300000
PO000428 | PRJ008 | V018 | Safety harnesses | 2025-10-28 | 2025-11-17 | 2025-11-21 | 26600000
PO000429 | PRJ009 | V029 | Diesel generator hire | 2025-04-30 | 2025-05-10 | 2025-05-16 | 34600000
PO000430 | PRJ010 | V040 | Tower crane hire | 2025-04-21 | 2025-05-16 | 2025-05-13 | 13300000
PO000431 | PRJ011 | V018 | Facade glazing panels | 2024-11-02 | 2024-12-13 | 2025-01-25 | 11200000
PO000432 | PRJ012 | V002 | Waterproofing membrane | 2026-05-04 | 2026-06-11 | 2026-06-09 | 21500000
PO000433 | PRJ013 | V013 | TMT rebar Fe500D | 2025-12-17 | 2026-01-10 | 2026-01-17 | 29300000
PO000434 | PRJ014 | V024 | OPC 53 grade cement | 2024-11-18 | 2024-12-14 | 2024-12-21 | 10800000
PO000435 | PRJ015 | V035 | Ready-mix concrete M35 | 2026-06-08 | 2026-07-16 | 2026-07-22 | 21900000
PO000436 | PRJ016 | V046 | Structural steel sections | 2025-11-22 | 2025-12-06 | 2025-12-11 | 18300000
PO000437 | PRJ017 | V057 | Aluminium formwork | 2025-08-19 | 2025-10-01 | 2025-10-05 | 21100000
PO000438 | PRJ018 | V008 | Fire-fighting piping | 2025-01-09 | 2025-02-20 | 2025-02-18 | 8600000
PO000439 | PRJ019 | V019 | Electrical cable trays | 2025-03-26 | 2025-04-11 | 2025-04-20 | 25800000
PO000440 | PRJ020 | V030 | Safety harnesses | 2025-04-05 | 2025-04-26 | 2025-04-26 | 12100000
PO000441 | PRJ021 | V025 | Diesel generator hire | 2025-04-08 | 2025-05-02 | 2025-06-11 | 9700000
PO000442 | PRJ022 | V052 | Tower crane hire | 2024-11-23 | 2024-12-04 | 2024-12-02 | 25500000
PO000443 | PRJ023 | V003 | Facade glazing panels | 2026-01-23 | 2026-02-12 | 2026-02-16 | 11800000
PO000444 | PRJ024 | V014 | Waterproofing membrane | 2026-04-15 | 2026-05-17 | 2026-05-13 | 24600000
PO000445 | PRJ025 | V025 | TMT rebar Fe500D | 2026-07-11 | 2026-07-26 | 2026-07-30 | 15200000
PO000446 | PRJ026 | V036 | OPC 53 grade cement | 2024-10-12 | 2024-11-02 | 2024-11-02 | 23500000
PO000447 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-09-16 | 2025-10-18 | 2025-10-23 | 15600000
PO000448 | PRJ028 | V058 | Structural steel sections | 2025-11-14 | 2025-12-06 | 2025-12-02 | 36900000
PO000449 | PRJ029 | V009 | Aluminium formwork | 2026-01-16 | 2026-02-17 | 2026-02-25 | 35000000
PO000450 | PRJ030 | V020 | Fire-fighting piping | 2025-10-13 | 2025-11-05 | 2025-11-07 | 18100000
PO000451 | PRJ001 | V003 | Electrical cable trays | 2025-02-28 | 2025-03-19 | 2025-04-18 | 37900000
PO000452 | PRJ002 | V042 | Safety harnesses | 2025-06-29 | 2025-07-11 | 2025-07-14 | 12900000
PO000453 | PRJ003 | V053 | Diesel generator hire | 2025-01-04 | 2025-02-14 | 2025-02-18 | 28500000
PO000454 | PRJ004 | V004 | Tower crane hire | 2025-10-14 | 2025-11-02 | 2025-11-01 | 18700000
PO000455 | PRJ005 | V015 | Facade glazing panels | 2025-01-12 | 2025-02-13 | 2025-02-12 | 18900000
PO000456 | PRJ006 | V026 | Waterproofing membrane | 2025-06-01 | 2025-06-29 | 2025-07-08 | 21500000
PO000457 | PRJ007 | V037 | TMT rebar Fe500D | 2026-06-10 | 2026-07-24 | 2026-07-28 | 14500000
PO000458 | PRJ008 | V048 | OPC 53 grade cement | 2025-05-12 | 2025-06-05 | 2025-06-06 | 11500000
PO000459 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-02-14 | 2025-03-30 | 2025-04-03 | 37800000
PO000460 | PRJ010 | V010 | Structural steel sections | 2025-03-14 | 2025-04-04 | 2025-04-12 | 21400000
PO000461 | PRJ011 | V007 | Aluminium formwork | 2026-04-11 | 2026-05-05 | 2026-05-24 | 14000000
PO000462 | PRJ012 | V032 | Fire-fighting piping | 2025-05-25 | 2025-06-24 | 2025-06-20 | 9000000
PO000463 | PRJ013 | V043 | Electrical cable trays | 2024-11-25 | 2024-12-18 | 2024-12-25 | 32600000
PO000464 | PRJ014 | V054 | Safety harnesses | 2024-11-16 | 2024-12-26 | 2025-01-01 | 27900000
PO000465 | PRJ015 | V005 | Diesel generator hire | 2026-03-06 | 2026-04-15 | 2026-04-20 | 30900000
PO000466 | PRJ016 | V016 | Tower crane hire | 2024-10-14 | 2024-11-21 | 2024-11-17 | 18500000
PO000467 | PRJ017 | V027 | Facade glazing panels | 2025-07-01 | 2025-08-10 | 2025-08-15 | 19200000
PO000468 | PRJ018 | V038 | Waterproofing membrane | 2026-04-15 | 2026-05-14 | 2026-05-15 | 9600000
PO000469 | PRJ019 | V049 | TMT rebar Fe500D | 2025-06-04 | 2025-07-10 | 2025-07-06 | 23900000
PO000470 | PRJ020 | V060 | OPC 53 grade cement | 2026-05-01 | 2026-06-13 | 2026-06-16 | 15400000
PO000471 | PRJ021 | V012 | Ready-mix concrete M35 | 2026-07-13 | 2026-08-01 | 2026-09-15 | 23600000
PO000472 | PRJ022 | V022 | Structural steel sections | 2026-03-30 | 2026-05-14 | 2026-05-18 | 21200000
PO000473 | PRJ023 | V033 | Aluminium formwork | 2025-01-18 | 2025-02-27 | 2025-02-25 | 35700000
PO000474 | PRJ024 | V044 | Fire-fighting piping | 2026-02-01 | 2026-03-11 | 2026-03-09 | 24800000
PO000475 | PRJ025 | V055 | Electrical cable trays | 2026-02-13 | 2026-03-03 | 2026-03-09 | 13400000
PO000476 | PRJ026 | V006 | Safety harnesses | 2025-01-02 | 2025-01-24 | 2025-02-01 | 18100000
PO000477 | PRJ027 | V017 | Diesel generator hire | 2025-04-11 | 2025-05-19 | 2025-05-17 | 23300000
PO000478 | PRJ028 | V028 | Tower crane hire | 2026-06-22 | 2026-08-06 | 2026-08-11 | 6700000
PO000479 | PRJ029 | V039 | Facade glazing panels | 2025-06-21 | 2025-07-20 | 2025-07-25 | 19800000
PO000480 | PRJ030 | V050 | Waterproofing membrane | 2026-04-15 | 2026-05-07 | 2026-05-16 | 29500000
PO000481 | PRJ001 | V018 | TMT rebar Fe500D | 2025-01-19 | 2025-02-14 | 2025-04-09 | 24000000
PO000482 | PRJ002 | V012 | OPC 53 grade cement | 2025-12-27 | 2026-01-13 | 2026-01-14 | 8200000
PO000483 | PRJ003 | V023 | Ready-mix concrete M35 | 2026-07-12 | 2026-08-01 | 2026-07-31 | 400000
PO000484 | PRJ004 | V034 | Structural steel sections | 2025-12-11 | 2026-01-22 | 2026-01-23 | 36600000
PO000485 | PRJ005 | V045 | Aluminium formwork | 2024-10-24 | 2024-11-30 | 2024-11-29 | 35000000
PO000486 | PRJ006 | V056 | Fire-fighting piping | 2025-10-12 | 2025-10-27 | 2025-11-03 | 17500000
PO000487 | PRJ007 | V007 | Electrical cable trays | 2025-12-15 | 2026-01-21 | 2026-01-26 | 6000000
PO000488 | PRJ008 | V018 | Safety harnesses | 2025-01-09 | 2025-02-03 | 2025-02-07 | 34700000
PO000489 | PRJ009 | V029 | Diesel generator hire | 2026-04-28 | 2026-05-26 | 2026-06-02 | 21000000
PO000490 | PRJ010 | V040 | Tower crane hire | 2025-02-12 | 2025-03-14 | 2025-03-21 | 12800000
PO000491 | PRJ011 | V025 | Facade glazing panels | 2025-09-12 | 2025-09-24 | 2025-10-20 | 200000
PO000492 | PRJ012 | V002 | Waterproofing membrane | 2026-05-10 | 2026-05-25 | 2026-05-24 | 19700000
PO000493 | PRJ013 | V013 | TMT rebar Fe500D | 2026-06-08 | 2026-07-06 | 2026-07-02 | 14500000
PO000494 | PRJ014 | V024 | OPC 53 grade cement | 2025-01-25 | 2025-02-10 | 2025-02-14 | 1500000
PO000495 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-01-26 | 2025-02-21 | 2025-02-28 | 10900000
PO000496 | PRJ016 | V046 | Structural steel sections | 2026-02-06 | 2026-03-12 | 2026-03-18 | 27100000
PO000497 | PRJ017 | V057 | Aluminium formwork | 2026-01-14 | 2026-01-31 | 2026-02-09 | 19200000
PO000498 | PRJ018 | V008 | Fire-fighting piping | 2025-12-08 | 2026-01-14 | 2026-01-21 | 5600000
PO000499 | PRJ019 | V019 | Electrical cable trays | 2026-02-03 | 2026-03-19 | 2026-03-28 | 18000000
PO000500 | PRJ020 | V030 | Safety harnesses | 2024-12-06 | 2025-01-01 | 2025-01-03 | 9400000
PO000501 | PRJ021 | V003 | Diesel generator hire | 2026-03-12 | 2026-03-27 | 2026-05-01 | 16300000
PO000502 | PRJ022 | V052 | Tower crane hire | 2026-04-15 | 2026-05-02 | 2026-05-06 | 22200000
PO000503 | PRJ023 | V003 | Facade glazing panels | 2025-06-25 | 2025-08-01 | 2025-08-09 | 18600000
PO000504 | PRJ024 | V014 | Waterproofing membrane | 2024-11-22 | 2024-12-10 | 2024-12-16 | 25600000
PO000505 | PRJ025 | V025 | TMT rebar Fe500D | 2026-02-10 | 2026-03-12 | 2026-03-10 | 8700000
PO000506 | PRJ026 | V036 | OPC 53 grade cement | 2026-02-04 | 2026-02-24 | 2026-03-02 | 36400000
PO000507 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-05-28 | 2025-06-09 | 2025-06-17 | 32900000
PO000508 | PRJ028 | V058 | Structural steel sections | 2025-03-17 | 2025-04-15 | 2025-04-20 | 36600000
PO000509 | PRJ029 | V009 | Aluminium formwork | 2025-05-10 | 2025-06-14 | 2025-06-15 | 27800000
PO000510 | PRJ030 | V020 | Fire-fighting piping | 2025-07-02 | 2025-08-08 | 2025-08-09 | 6100000
PO000511 | PRJ001 | V007 | Electrical cable trays | 2025-08-10 | 2025-09-01 | 2025-10-19 | 34300000
PO000512 | PRJ002 | V042 | Safety harnesses | 2025-04-02 | 2025-05-11 | 2025-05-12 | 23300000
PO000513 | PRJ003 | V053 | Diesel generator hire | 2024-11-28 | 2024-12-15 | 2024-12-11 | 37600000
PO000514 | PRJ004 | V004 | Tower crane hire | 2025-12-01 | 2025-12-12 | 2025-12-16 | 12500000
PO000515 | PRJ005 | V015 | Facade glazing panels | 2026-05-17 | 2026-06-01 | 2026-05-31 | 36600000
PO000516 | PRJ006 | V026 | Waterproofing membrane | 2024-12-15 | 2025-01-09 | 2025-01-15 | 7200000
PO000517 | PRJ007 | V037 | TMT rebar Fe500D | 2025-12-28 | 2026-02-02 | 2026-02-11 | 13300000
PO000518 | PRJ008 | V048 | OPC 53 grade cement | 2025-11-08 | 2025-11-18 | 2025-11-22 | 34600000
PO000519 | PRJ009 | V059 | Ready-mix concrete M35 | 2024-12-19 | 2025-01-07 | 2025-01-08 | 34100000
PO000520 | PRJ010 | V010 | Structural steel sections | 2026-05-19 | 2026-06-26 | 2026-06-30 | 36500000
PO000521 | PRJ011 | V012 | Aluminium formwork | 2026-04-23 | 2026-05-07 | 2026-06-14 | 10600000
PO000522 | PRJ012 | V032 | Fire-fighting piping | 2026-05-31 | 2026-07-12 | 2026-07-08 | 9100000
PO000523 | PRJ013 | V043 | Electrical cable trays | 2025-05-11 | 2025-06-01 | 2025-06-07 | 36800000
PO000524 | PRJ014 | V054 | Safety harnesses | 2025-03-12 | 2025-04-03 | 2025-04-12 | 2200000
PO000525 | PRJ015 | V005 | Diesel generator hire | 2025-01-30 | 2025-03-03 | 2025-03-07 | 14200000
PO000526 | PRJ016 | V016 | Tower crane hire | 2024-10-30 | 2024-12-14 | 2024-12-22 | 3700000
PO000527 | PRJ017 | V027 | Facade glazing panels | 2025-11-24 | 2026-01-04 | 2026-01-12 | 20900000
PO000528 | PRJ018 | V038 | Waterproofing membrane | 2026-05-13 | 2026-06-26 | 2026-06-26 | 17800000
PO000529 | PRJ019 | V049 | TMT rebar Fe500D | 2025-06-04 | 2025-06-29 | 2025-07-07 | 32200000
PO000530 | PRJ020 | V060 | OPC 53 grade cement | 2026-03-29 | 2026-04-16 | 2026-04-19 | 12900000
PO000531 | PRJ021 | V018 | Ready-mix concrete M35 | 2025-08-27 | 2025-10-10 | 2025-11-02 | 36400000
PO000532 | PRJ022 | V022 | Structural steel sections | 2025-05-05 | 2025-05-31 | 2025-06-05 | 37200000
PO000533 | PRJ023 | V033 | Aluminium formwork | 2025-09-18 | 2025-10-07 | 2025-10-10 | 20500000
PO000534 | PRJ024 | V044 | Fire-fighting piping | 2025-01-23 | 2025-02-10 | 2025-02-07 | 3200000
PO000535 | PRJ025 | V055 | Electrical cable trays | 2025-05-14 | 2025-06-14 | 2025-06-23 | 21800000
PO000536 | PRJ026 | V006 | Safety harnesses | 2026-01-31 | 2026-02-26 | 2026-03-07 | 31500000
PO000537 | PRJ027 | V017 | Diesel generator hire | 2025-04-26 | 2025-05-24 | 2025-05-27 | 16100000
PO000538 | PRJ028 | V028 | Tower crane hire | 2025-04-21 | 2025-05-14 | 2025-05-15 | 20000000
PO000539 | PRJ029 | V039 | Facade glazing panels | 2025-06-29 | 2025-07-20 | 2025-07-22 | 14900000
PO000540 | PRJ030 | V050 | Waterproofing membrane | 2025-09-15 | 2025-10-01 | 2025-10-01 | 18100000
PO000541 | PRJ001 | V025 | TMT rebar Fe500D | 2025-11-18 | 2025-11-28 | 2025-12-31 | 800000
PO000542 | PRJ002 | V012 | OPC 53 grade cement | 2026-05-09 | 2026-05-29 | 2026-06-03 | 23800000
PO000543 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-08-24 | 2025-09-20 | 2025-09-23 | 29100000
PO000544 | PRJ004 | V034 | Structural steel sections | 2026-04-30 | 2026-05-30 | 2026-06-06 | 7700000
PO000545 | PRJ005 | V045 | Aluminium formwork | 2026-03-21 | 2026-04-16 | 2026-04-21 | 26200000
PO000546 | PRJ006 | V056 | Fire-fighting piping | 2025-07-25 | 2025-08-06 | 2025-08-14 | 17400000
PO000547 | PRJ007 | V007 | Electrical cable trays | 2024-10-15 | 2024-11-13 | 2024-11-11 | 29600000
PO000548 | PRJ008 | V018 | Safety harnesses | 2026-07-06 | 2026-08-16 | 2026-08-25 | 24300000
PO000549 | PRJ009 | V029 | Diesel generator hire | 2024-11-14 | 2024-12-20 | 2024-12-27 | 33600000
PO000550 | PRJ010 | V040 | Tower crane hire | 2024-11-15 | 2024-11-28 | 2024-11-27 | 14600000
PO000551 | PRJ011 | V003 | Facade glazing panels | 2026-02-15 | 2026-03-14 | 2026-04-11 | 32400000
PO000552 | PRJ012 | V002 | Waterproofing membrane | 2025-10-06 | 2025-10-28 | 2025-11-05 | 17000000
PO000553 | PRJ013 | V013 | TMT rebar Fe500D | 2026-07-06 | 2026-08-05 | 2026-08-01 | 20100000
PO000554 | PRJ014 | V024 | OPC 53 grade cement | 2025-12-28 | 2026-01-07 | 2026-01-03 | 8400000
PO000555 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-11-18 | 2025-12-02 | 2025-12-05 | 17900000
PO000556 | PRJ016 | V046 | Structural steel sections | 2025-08-19 | 2025-09-10 | 2025-09-10 | 4800000
PO000557 | PRJ017 | V057 | Aluminium formwork | 2025-01-05 | 2025-02-06 | 2025-02-09 | 21400000
PO000558 | PRJ018 | V008 | Fire-fighting piping | 2026-02-24 | 2026-03-10 | 2026-03-06 | 20400000
PO000559 | PRJ019 | V019 | Electrical cable trays | 2024-11-24 | 2024-12-09 | 2024-12-13 | 30900000
PO000560 | PRJ020 | V030 | Safety harnesses | 2024-12-17 | 2024-12-31 | 2025-01-08 | 13500000
PO000561 | PRJ021 | V007 | Diesel generator hire | 2025-08-31 | 2025-09-29 | 2025-11-11 | 32900000
PO000562 | PRJ022 | V052 | Tower crane hire | 2026-02-01 | 2026-03-10 | 2026-03-10 | 16400000
PO000563 | PRJ023 | V003 | Facade glazing panels | 2025-09-18 | 2025-10-25 | 2025-10-21 | 29400000
PO000564 | PRJ024 | V014 | Waterproofing membrane | 2025-10-14 | 2025-11-25 | 2025-11-26 | 36300000
PO000565 | PRJ025 | V025 | TMT rebar Fe500D | 2025-01-26 | 2025-02-11 | 2025-02-07 | 5600000
PO000566 | PRJ026 | V036 | OPC 53 grade cement | 2026-07-03 | 2026-08-09 | 2026-08-15 | 14200000
PO000567 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-09-06 | 2025-09-27 | 2025-09-25 | 13900000
PO000568 | PRJ028 | V058 | Structural steel sections | 2024-12-25 | 2025-01-24 | 2025-02-02 | 16900000
PO000569 | PRJ029 | V009 | Aluminium formwork | 2026-06-29 | 2026-07-26 | 2026-07-25 | 7200000
PO000570 | PRJ030 | V020 | Fire-fighting piping | 2026-06-11 | 2026-06-28 | 2026-07-04 | 18100000
PO000571 | PRJ001 | V012 | Electrical cable trays | 2025-07-13 | 2025-08-14 | 2025-09-01 | 14000000
PO000572 | PRJ002 | V042 | Safety harnesses | 2026-01-01 | 2026-01-28 | 2026-01-26 | 36200000
PO000573 | PRJ003 | V053 | Diesel generator hire | 2025-10-21 | 2025-11-09 | 2025-11-11 | 26100000
PO000574 | PRJ004 | V004 | Tower crane hire | 2024-11-08 | 2024-11-28 | 2024-12-03 | 11800000
PO000575 | PRJ005 | V015 | Facade glazing panels | 2026-05-18 | 2026-06-28 | 2026-07-06 | 8600000
PO000576 | PRJ006 | V026 | Waterproofing membrane | 2025-06-18 | 2025-07-14 | 2025-07-11 | 29700000
PO000577 | PRJ007 | V037 | TMT rebar Fe500D | 2025-01-28 | 2025-03-07 | 2025-03-12 | 17000000
PO000578 | PRJ008 | V048 | OPC 53 grade cement | 2024-12-10 | 2025-01-07 | 2025-01-14 | 13300000
PO000579 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-03-03 | 2025-03-21 | 2025-03-22 | 1600000
PO000580 | PRJ010 | V010 | Structural steel sections | 2026-01-05 | 2026-02-07 | 2026-02-09 | 34100000
PO000581 | PRJ011 | V018 | Aluminium formwork | 2025-03-01 | 2025-03-25 | 2025-05-09 | 19500000
PO000582 | PRJ012 | V032 | Fire-fighting piping | 2025-07-04 | 2025-07-20 | 2025-07-26 | 33600000
PO000583 | PRJ013 | V043 | Electrical cable trays | 2025-05-19 | 2025-06-26 | 2025-06-28 | 2500000
PO000584 | PRJ014 | V054 | Safety harnesses | 2025-01-23 | 2025-02-10 | 2025-02-14 | 4400000
PO000585 | PRJ015 | V005 | Diesel generator hire | 2025-05-03 | 2025-06-14 | 2025-06-21 | 6100000
PO000586 | PRJ016 | V016 | Tower crane hire | 2025-04-28 | 2025-05-20 | 2025-05-16 | 22000000
PO000587 | PRJ017 | V027 | Facade glazing panels | 2025-04-12 | 2025-05-27 | 2025-05-27 | 15800000
PO000588 | PRJ018 | V038 | Waterproofing membrane | 2024-12-20 | 2025-01-02 | 2025-01-05 | 12200000
PO000589 | PRJ019 | V049 | TMT rebar Fe500D | 2026-05-11 | 2026-06-15 | 2026-06-17 | 5700000
PO000590 | PRJ020 | V060 | OPC 53 grade cement | 2025-12-03 | 2025-12-28 | 2025-12-29 | 19800000
PO000591 | PRJ021 | V025 | Ready-mix concrete M35 | 2025-06-15 | 2025-07-07 | 2025-08-08 | 31600000
PO000592 | PRJ022 | V022 | Structural steel sections | 2025-04-28 | 2025-05-27 | 2025-06-02 | 36300000
PO000593 | PRJ023 | V033 | Aluminium formwork | 2025-07-13 | 2025-08-26 | 2025-08-26 | 30800000
PO000594 | PRJ024 | V044 | Fire-fighting piping | 2025-05-15 | 2025-06-06 | 2025-06-07 | 35100000
PO000595 | PRJ025 | V055 | Electrical cable trays | 2026-01-28 | 2026-02-15 | 2026-02-15 | 24600000
PO000596 | PRJ026 | V006 | Safety harnesses | 2025-07-09 | 2025-07-26 | 2025-07-29 | 35700000
PO000597 | PRJ027 | V017 | Diesel generator hire | 2026-05-29 | 2026-06-08 | 2026-06-16 | 14200000
PO000598 | PRJ028 | V028 | Tower crane hire | 2025-10-30 | 2025-11-23 | 2025-12-02 | 28000000
PO000599 | PRJ029 | V039 | Facade glazing panels | 2025-08-31 | 2025-10-01 | 2025-10-06 | 2000000
PO000600 | PRJ030 | V050 | Waterproofing membrane | 2025-03-23 | 2025-04-26 | 2025-04-30 | 25600000
PO000601 | PRJ001 | V003 | TMT rebar Fe500D | 2025-06-09 | 2025-07-07 | 2025-07-25 | 25400000
PO000602 | PRJ002 | V012 | OPC 53 grade cement | 2025-10-05 | 2025-11-14 | 2025-11-19 | 26000000
PO000603 | PRJ003 | V023 | Ready-mix concrete M35 | 2026-02-10 | 2026-03-22 | 2026-03-28 | 34000000
PO000604 | PRJ004 | V034 | Structural steel sections | 2024-10-03 | 2024-11-02 | 2024-11-05 | 13000000
PO000605 | PRJ005 | V045 | Aluminium formwork | 2025-06-05 | 2025-07-06 | 2025-07-12 | 32900000
PO000606 | PRJ006 | V056 | Fire-fighting piping | 2025-01-25 | 2025-02-19 | 2025-02-17 | 26400000
PO000607 | PRJ007 | V007 | Electrical cable trays | 2025-06-27 | 2025-07-29 | 2025-08-02 | 17400000
PO000608 | PRJ008 | V018 | Safety harnesses | 2026-04-22 | 2026-05-16 | 2026-05-23 | 13600000
PO000609 | PRJ009 | V029 | Diesel generator hire | 2026-02-10 | 2026-03-08 | 2026-03-16 | 4100000
PO000610 | PRJ010 | V040 | Tower crane hire | 2025-11-21 | 2025-12-24 | 2025-12-27 | 25500000
PO000611 | PRJ011 | V007 | Facade glazing panels | 2026-03-14 | 2026-03-28 | 2026-05-16 | 29700000
PO000612 | PRJ012 | V002 | Waterproofing membrane | 2025-04-01 | 2025-05-02 | 2025-05-05 | 2900000
PO000613 | PRJ013 | V013 | TMT rebar Fe500D | 2025-08-25 | 2025-09-18 | 2025-09-19 | 26700000
PO000614 | PRJ014 | V024 | OPC 53 grade cement | 2026-06-05 | 2026-06-21 | 2026-06-26 | 23200000
PO000615 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-09-15 | 2025-10-22 | 2025-10-22 | 12200000
PO000616 | PRJ016 | V046 | Structural steel sections | 2026-06-29 | 2026-08-12 | 2026-08-18 | 700000
PO000617 | PRJ017 | V057 | Aluminium formwork | 2025-11-05 | 2025-11-21 | 2025-11-20 | 3800000
PO000618 | PRJ018 | V008 | Fire-fighting piping | 2025-03-05 | 2025-04-19 | 2025-04-21 | 28300000
PO000619 | PRJ019 | V019 | Electrical cable trays | 2026-05-07 | 2026-05-20 | 2026-05-26 | 8500000
PO000620 | PRJ020 | V030 | Safety harnesses | 2026-05-30 | 2026-07-05 | 2026-07-08 | 7500000
PO000621 | PRJ021 | V012 | Diesel generator hire | 2026-04-26 | 2026-06-04 | 2026-07-21 | 8000000
PO000622 | PRJ022 | V052 | Tower crane hire | 2025-05-08 | 2025-05-19 | 2025-05-22 | 300000
PO000623 | PRJ023 | V003 | Facade glazing panels | 2025-06-19 | 2025-07-01 | 2025-06-27 | 16800000
PO000624 | PRJ024 | V014 | Waterproofing membrane | 2025-04-28 | 2025-06-08 | 2025-06-17 | 25900000
PO000625 | PRJ025 | V025 | TMT rebar Fe500D | 2025-06-23 | 2025-08-04 | 2025-08-07 | 18500000
PO000626 | PRJ026 | V036 | OPC 53 grade cement | 2025-04-07 | 2025-04-23 | 2025-04-27 | 25700000
PO000627 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-04-27 | 2025-05-21 | 2025-05-19 | 26600000
PO000628 | PRJ028 | V058 | Structural steel sections | 2025-12-31 | 2026-01-31 | 2026-02-04 | 25300000
PO000629 | PRJ029 | V009 | Aluminium formwork | 2026-01-28 | 2026-02-12 | 2026-02-14 | 13800000
PO000630 | PRJ030 | V020 | Fire-fighting piping | 2025-04-21 | 2025-05-12 | 2025-05-12 | 6600000
PO000631 | PRJ001 | V018 | Electrical cable trays | 2025-04-22 | 2025-05-24 | 2025-06-12 | 23500000
PO000632 | PRJ002 | V042 | Safety harnesses | 2025-04-26 | 2025-05-07 | 2025-05-09 | 18900000
PO000633 | PRJ003 | V053 | Diesel generator hire | 2024-11-21 | 2024-12-31 | 2025-01-02 | 300000
PO000634 | PRJ004 | V004 | Tower crane hire | 2025-01-01 | 2025-02-01 | 2025-01-28 | 33000000
PO000635 | PRJ005 | V015 | Facade glazing panels | 2026-04-03 | 2026-04-14 | 2026-04-19 | 4400000
PO000636 | PRJ006 | V026 | Waterproofing membrane | 2025-11-06 | 2025-11-16 | 2025-11-18 | 1300000
PO000637 | PRJ007 | V037 | TMT rebar Fe500D | 2025-04-19 | 2025-05-31 | 2025-06-06 | 24300000
PO000638 | PRJ008 | V048 | OPC 53 grade cement | 2026-06-20 | 2026-07-09 | 2026-07-07 | 22100000
PO000639 | PRJ009 | V059 | Ready-mix concrete M35 | 2026-06-20 | 2026-07-11 | 2026-07-10 | 31500000
PO000640 | PRJ010 | V010 | Structural steel sections | 2026-02-17 | 2026-03-06 | 2026-03-13 | 27300000
PO000641 | PRJ011 | V025 | Aluminium formwork | 2024-10-20 | 2024-11-23 | 2024-12-18 | 19700000
PO000642 | PRJ012 | V032 | Fire-fighting piping | 2025-04-10 | 2025-04-23 | 2025-04-29 | 13900000
PO000643 | PRJ013 | V043 | Electrical cable trays | 2026-02-10 | 2026-03-11 | 2026-03-15 | 16800000
PO000644 | PRJ014 | V054 | Safety harnesses | 2026-01-22 | 2026-02-04 | 2026-02-10 | 10400000
PO000645 | PRJ015 | V005 | Diesel generator hire | 2025-02-27 | 2025-03-10 | 2025-03-11 | 24400000
PO000646 | PRJ016 | V016 | Tower crane hire | 2025-10-28 | 2025-11-15 | 2025-11-13 | 23800000
PO000647 | PRJ017 | V027 | Facade glazing panels | 2025-02-08 | 2025-03-08 | 2025-03-11 | 8000000
PO000648 | PRJ018 | V038 | Waterproofing membrane | 2025-03-09 | 2025-04-13 | 2025-04-12 | 28200000
PO000649 | PRJ019 | V049 | TMT rebar Fe500D | 2026-05-04 | 2026-05-21 | 2026-05-22 | 8300000
PO000650 | PRJ020 | V060 | OPC 53 grade cement | 2025-08-23 | 2025-09-27 | 2025-10-06 | 9100000
PO000651 | PRJ021 | V003 | Ready-mix concrete M35 | 2026-03-29 | 2026-05-03 | 2026-05-27 | 23900000
PO000652 | PRJ022 | V022 | Structural steel sections | 2025-06-10 | 2025-07-24 | 2025-07-31 | 20200000
PO000653 | PRJ023 | V033 | Aluminium formwork | 2025-05-28 | 2025-06-26 | 2025-06-29 | 18500000
PO000654 | PRJ024 | V044 | Fire-fighting piping | 2026-07-04 | 2026-07-27 | 2026-08-04 | 9900000
PO000655 | PRJ025 | V055 | Electrical cable trays | 2025-05-04 | 2025-06-07 | 2025-06-13 | 13200000
PO000656 | PRJ026 | V006 | Safety harnesses | 2025-02-10 | 2025-03-09 | 2025-03-07 | 4700000
PO000657 | PRJ027 | V017 | Diesel generator hire | 2025-05-23 | 2025-07-03 | 2025-06-29 | 28000000
PO000658 | PRJ028 | V028 | Tower crane hire | 2025-11-10 | 2025-12-06 | 2025-12-14 | 34100000
PO000659 | PRJ029 | V039 | Facade glazing panels | 2025-10-01 | 2025-10-24 | 2025-10-23 | 25800000
PO000660 | PRJ030 | V050 | Waterproofing membrane | 2026-02-26 | 2026-03-27 | 2026-03-30 | 2900000
PO000661 | PRJ001 | V007 | TMT rebar Fe500D | 2025-10-03 | 2025-10-21 | 2025-11-10 | 24600000
PO000662 | PRJ002 | V012 | OPC 53 grade cement | 2026-05-17 | 2026-06-14 | 2026-06-10 | 37500000
PO000663 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-10-07 | 2025-10-22 | 2025-10-22 | 34000000
PO000664 | PRJ004 | V034 | Structural steel sections | 2025-03-19 | 2025-04-12 | 2025-04-17 | 28600000
PO000665 | PRJ005 | V045 | Aluminium formwork | 2025-09-15 | 2025-10-19 | 2025-10-15 | 20900000
PO000666 | PRJ006 | V056 | Fire-fighting piping | 2025-12-03 | 2026-01-02 | 2026-01-06 | 16500000
PO000667 | PRJ007 | V007 | Electrical cable trays | 2026-02-26 | 2026-04-12 | 2026-04-12 | 34700000
PO000668 | PRJ008 | V018 | Safety harnesses | 2025-04-13 | 2025-05-05 | 2025-05-05 | 9400000
PO000669 | PRJ009 | V029 | Diesel generator hire | 2025-12-22 | 2026-02-05 | 2026-02-14 | 15000000
PO000670 | PRJ010 | V040 | Tower crane hire | 2025-08-17 | 2025-08-28 | 2025-08-27 | 29400000
PO000671 | PRJ011 | V012 | Facade glazing panels | 2025-02-25 | 2025-03-27 | 2025-05-20 | 29100000
PO000672 | PRJ012 | V002 | Waterproofing membrane | 2025-08-19 | 2025-09-08 | 2025-09-08 | 23600000
PO000673 | PRJ013 | V013 | TMT rebar Fe500D | 2025-05-16 | 2025-05-31 | 2025-05-27 | 31000000
PO000674 | PRJ014 | V024 | OPC 53 grade cement | 2026-04-07 | 2026-05-05 | 2026-05-08 | 26100000
PO000675 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-04-14 | 2025-05-03 | 2025-05-06 | 8300000
PO000676 | PRJ016 | V046 | Structural steel sections | 2025-02-18 | 2025-03-09 | 2025-03-10 | 23600000
PO000677 | PRJ017 | V057 | Aluminium formwork | 2026-06-09 | 2026-07-09 | 2026-07-18 | 25800000
PO000678 | PRJ018 | V008 | Fire-fighting piping | 2026-05-31 | 2026-07-09 | 2026-07-16 | 20600000
PO000679 | PRJ019 | V019 | Electrical cable trays | 2026-02-01 | 2026-02-24 | 2026-03-01 | 35700000
PO000680 | PRJ020 | V030 | Safety harnesses | 2026-06-30 | 2026-07-27 | 2026-07-23 | 25300000
PO000681 | PRJ021 | V018 | Diesel generator hire | 2025-07-25 | 2025-08-26 | 2025-09-29 | 18000000
PO000682 | PRJ022 | V052 | Tower crane hire | 2025-06-19 | 2025-07-05 | 2025-07-02 | 21100000
PO000683 | PRJ023 | V003 | Facade glazing panels | 2025-11-10 | 2025-12-25 | 2025-12-21 | 19700000
PO000684 | PRJ024 | V014 | Waterproofing membrane | 2025-12-31 | 2026-01-27 | 2026-02-03 | 17500000
PO000685 | PRJ025 | V025 | TMT rebar Fe500D | 2026-01-16 | 2026-02-22 | 2026-02-18 | 24800000
PO000686 | PRJ026 | V036 | OPC 53 grade cement | 2025-12-23 | 2026-01-16 | 2026-01-14 | 30200000
PO000687 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-05-29 | 2025-06-10 | 2025-06-18 | 2000000
PO000688 | PRJ028 | V058 | Structural steel sections | 2025-05-13 | 2025-05-25 | 2025-05-26 | 13600000
PO000689 | PRJ029 | V009 | Aluminium formwork | 2026-03-23 | 2026-04-22 | 2026-04-29 | 33400000
PO000690 | PRJ030 | V020 | Fire-fighting piping | 2025-01-18 | 2025-02-06 | 2025-02-06 | 3600000
PO000691 | PRJ001 | V025 | Electrical cable trays | 2025-11-05 | 2025-12-19 | 2026-01-28 | 23700000
PO000692 | PRJ002 | V042 | Safety harnesses | 2026-05-07 | 2026-05-22 | 2026-05-23 | 6600000
PO000693 | PRJ003 | V053 | Diesel generator hire | 2025-01-14 | 2025-02-17 | 2025-02-15 | 9200000
PO000694 | PRJ004 | V004 | Tower crane hire | 2024-12-08 | 2025-01-21 | 2025-01-27 | 30000000
PO000695 | PRJ005 | V015 | Facade glazing panels | 2025-01-04 | 2025-02-02 | 2025-02-03 | 28100000
PO000696 | PRJ006 | V026 | Waterproofing membrane | 2026-06-27 | 2026-07-09 | 2026-07-10 | 23500000
PO000697 | PRJ007 | V037 | TMT rebar Fe500D | 2025-08-30 | 2025-09-21 | 2025-09-27 | 13400000
PO000698 | PRJ008 | V048 | OPC 53 grade cement | 2025-05-31 | 2025-06-11 | 2025-06-09 | 700000
PO000699 | PRJ009 | V059 | Ready-mix concrete M35 | 2025-01-20 | 2025-02-13 | 2025-02-17 | 9200000
PO000700 | PRJ010 | V010 | Structural steel sections | 2025-05-02 | 2025-06-13 | 2025-06-14 | 9900000
PO000701 | PRJ011 | V003 | Aluminium formwork | 2025-07-01 | 2025-07-15 | 2025-08-07 | 8600000
PO000702 | PRJ012 | V032 | Fire-fighting piping | 2026-03-02 | 2026-04-07 | 2026-04-04 | 10000000
PO000703 | PRJ013 | V043 | Electrical cable trays | 2026-03-11 | 2026-04-17 | 2026-04-14 | 7000000
PO000704 | PRJ014 | V054 | Safety harnesses | 2025-09-30 | 2025-10-14 | 2025-10-23 | 29100000
PO000705 | PRJ015 | V005 | Diesel generator hire | 2024-11-22 | 2024-12-17 | 2024-12-22 | 7300000
PO000706 | PRJ016 | V016 | Tower crane hire | 2024-10-23 | 2024-12-04 | 2024-12-04 | 14700000
PO000707 | PRJ017 | V027 | Facade glazing panels | 2026-05-12 | 2026-06-08 | 2026-06-04 | 30700000
PO000708 | PRJ018 | V038 | Waterproofing membrane | 2025-08-22 | 2025-09-07 | 2025-09-12 | 6100000
PO000709 | PRJ019 | V049 | TMT rebar Fe500D | 2026-07-12 | 2026-07-23 | 2026-08-01 | 14800000
PO000710 | PRJ020 | V060 | OPC 53 grade cement | 2024-10-27 | 2024-12-05 | 2024-12-07 | 17400000
PO000711 | PRJ021 | V007 | Ready-mix concrete M35 | 2026-03-15 | 2026-04-11 | 2026-05-19 | 18000000
PO000712 | PRJ022 | V022 | Structural steel sections | 2025-09-28 | 2025-10-18 | 2025-10-16 | 17600000
PO000713 | PRJ023 | V033 | Aluminium formwork | 2025-06-18 | 2025-08-02 | 2025-08-07 | 21600000
PO000714 | PRJ024 | V044 | Fire-fighting piping | 2025-11-20 | 2025-12-02 | 2025-12-11 | 28500000
PO000715 | PRJ025 | V055 | Electrical cable trays | 2025-09-16 | 2025-10-23 | 2025-10-24 | 26200000
PO000716 | PRJ026 | V006 | Safety harnesses | 2024-12-11 | 2025-01-21 | 2025-01-17 | 10300000
PO000717 | PRJ027 | V017 | Diesel generator hire | 2025-12-06 | 2026-01-17 | 2026-01-15 | 22800000
PO000718 | PRJ028 | V028 | Tower crane hire | 2025-08-22 | 2025-09-20 | 2025-09-21 | 28100000
PO000719 | PRJ029 | V039 | Facade glazing panels | 2025-12-18 | 2026-02-01 | 2026-02-10 | 32300000
PO000720 | PRJ030 | V050 | Waterproofing membrane | 2025-02-22 | 2025-04-08 | 2025-04-10 | 27100000
PO000721 | PRJ001 | V012 | TMT rebar Fe500D | 2024-12-20 | 2025-01-14 | 2025-03-04 | 5700000
PO000722 | PRJ002 | V012 | OPC 53 grade cement | 2026-06-08 | 2026-07-11 | 2026-07-15 | 7900000
PO000723 | PRJ003 | V023 | Ready-mix concrete M35 | 2024-11-27 | 2024-12-12 | 2024-12-18 | 34300000
PO000724 | PRJ004 | V034 | Structural steel sections | 2024-12-16 | 2025-01-25 | 2025-01-26 | 34100000
PO000725 | PRJ005 | V045 | Aluminium formwork | 2026-01-16 | 2026-02-27 | 2026-02-28 | 11100000
PO000726 | PRJ006 | V056 | Fire-fighting piping | 2026-02-01 | 2026-03-06 | 2026-03-04 | 15200000
PO000727 | PRJ007 | V007 | Electrical cable trays | 2025-08-31 | 2025-09-10 | 2025-09-09 | 14100000
PO000728 | PRJ008 | V018 | Safety harnesses | 2026-06-19 | 2026-06-30 | 2026-07-08 | 9800000
PO000729 | PRJ009 | V029 | Diesel generator hire | 2026-03-20 | 2026-04-13 | 2026-04-18 | 14900000
PO000730 | PRJ010 | V040 | Tower crane hire | 2025-04-14 | 2025-05-26 | 2025-05-31 | 16500000
PO000731 | PRJ011 | V018 | Facade glazing panels | 2025-08-10 | 2025-09-18 | 2025-10-27 | 26600000
PO000732 | PRJ012 | V002 | Waterproofing membrane | 2025-08-21 | 2025-09-07 | 2025-09-10 | 37200000
PO000733 | PRJ013 | V013 | TMT rebar Fe500D | 2026-06-28 | 2026-08-05 | 2026-08-09 | 600000
PO000734 | PRJ014 | V024 | OPC 53 grade cement | 2026-03-26 | 2026-04-28 | 2026-04-25 | 7100000
PO000735 | PRJ015 | V035 | Ready-mix concrete M35 | 2025-09-16 | 2025-09-28 | 2025-09-26 | 6900000
PO000736 | PRJ016 | V046 | Structural steel sections | 2026-01-22 | 2026-02-03 | 2026-02-06 | 30300000
PO000737 | PRJ017 | V057 | Aluminium formwork | 2025-01-28 | 2025-02-21 | 2025-03-01 | 27600000
PO000738 | PRJ018 | V008 | Fire-fighting piping | 2025-09-11 | 2025-09-29 | 2025-10-08 | 11400000
PO000739 | PRJ019 | V019 | Electrical cable trays | 2026-01-12 | 2026-02-23 | 2026-02-24 | 19100000
PO000740 | PRJ020 | V030 | Safety harnesses | 2025-04-10 | 2025-04-29 | 2025-05-03 | 18400000
PO000741 | PRJ021 | V025 | Diesel generator hire | 2025-06-27 | 2025-08-09 | 2025-09-02 | 37900000
PO000742 | PRJ022 | V052 | Tower crane hire | 2026-01-09 | 2026-02-11 | 2026-02-12 | 13100000
PO000743 | PRJ023 | V003 | Facade glazing panels | 2025-10-14 | 2025-11-19 | 2025-11-28 | 32800000
PO000744 | PRJ024 | V014 | Waterproofing membrane | 2025-01-25 | 2025-02-26 | 2025-02-28 | 10900000
PO000745 | PRJ025 | V025 | TMT rebar Fe500D | 2025-09-14 | 2025-10-01 | 2025-10-06 | 4400000
PO000746 | PRJ026 | V036 | OPC 53 grade cement | 2024-12-27 | 2025-02-06 | 2025-02-04 | 37400000
PO000747 | PRJ027 | V047 | Ready-mix concrete M35 | 2025-04-19 | 2025-05-10 | 2025-05-12 | 18600000
PO000748 | PRJ028 | V058 | Structural steel sections | 2025-05-01 | 2025-06-15 | 2025-06-22 | 1800000
PO000749 | PRJ029 | V009 | Aluminium formwork | 2025-09-29 | 2025-10-27 | 2025-11-01 | 13500000
PO000750 | PRJ030 | V020 | Fire-fighting piping | 2026-02-03 | 2026-02-27 | 2026-02-23 | 18400000
PO000751 | PRJ001 | V003 | Electrical cable trays | 2025-08-01 | 2025-08-16 | 2025-10-07 | 15900000
PO000752 | PRJ002 | V042 | Safety harnesses | 2024-11-02 | 2024-11-25 | 2024-11-28 | 500000
PO000753 | PRJ003 | V053 | Diesel generator hire | 2025-08-06 | 2025-09-10 | 2025-09-12 | 25500000
PO000754 | PRJ004 | V004 | Tower crane hire | 2024-10-29 | 2024-12-03 | 2024-12-01 | 23200000
PO000755 | PRJ005 | V015 | Facade glazing panels | 2024-12-25 | 2025-02-03 | 2025-02-06 | 18400000
PO000756 | PRJ006 | V026 | Waterproofing membrane | 2024-11-01 | 2024-11-25 | 2024-12-03 | 7900000
PO000757 | PRJ007 | V037 | TMT rebar Fe500D | 2024-10-23 | 2024-11-30 | 2024-12-02 | 28300000
PO000758 | PRJ008 | V048 | OPC 53 grade cement | 2025-09-26 | 2025-10-21 | 2025-10-19 | 19600000
PO000759 | PRJ009 | V059 | Ready-mix concrete M35 | 2026-06-15 | 2026-07-04 | 2026-07-07 | 2000000
PO000760 | PRJ010 | V010 | Structural steel sections | 2025-08-18 | 2025-09-28 | 2025-09-26 | 27400000
PO000761 | PRJ011 | V007 | Aluminium formwork | 2025-02-06 | 2025-03-18 | 2025-04-07 | 31300000
PO000762 | PRJ012 | V032 | Fire-fighting piping | 2025-01-24 | 2025-03-05 | 2025-03-11 | 26000000
PO000763 | PRJ013 | V043 | Electrical cable trays | 2026-07-13 | 2026-08-17 | 2026-08-17 | 37600000
PO000764 | PRJ014 | V054 | Safety harnesses | 2024-12-10 | 2024-12-22 | 2024-12-25 | 8200000
PO000765 | PRJ015 | V005 | Diesel generator hire | 2025-09-29 | 2025-11-12 | 2025-11-18 | 4800000
PO000766 | PRJ016 | V016 | Tower crane hire | 2026-02-14 | 2026-03-03 | 2026-03-07 | 300000
PO000767 | PRJ017 | V027 | Facade glazing panels | 2026-02-15 | 2026-03-16 | 2026-03-16 | 34200000
PO000768 | PRJ018 | V038 | Waterproofing membrane | 2025-07-01 | 2025-07-20 | 2025-07-26 | 13300000
PO000769 | PRJ019 | V049 | TMT rebar Fe500D | 2026-01-15 | 2026-02-27 | 2026-03-08 | 4800000
PO000770 | PRJ020 | V060 | OPC 53 grade cement | 2024-12-12 | 2024-12-31 | 2025-01-01 | 23300000
PO000771 | PRJ021 | V012 | Ready-mix concrete M35 | 2024-10-12 | 2024-11-06 | 2024-12-24 | 300000
PO000772 | PRJ022 | V022 | Structural steel sections | 2025-04-15 | 2025-05-17 | 2025-05-20 | 31200000
PO000773 | PRJ023 | V033 | Aluminium formwork | 2024-11-19 | 2024-12-19 | 2024-12-19 | 17700000
PO000774 | PRJ024 | V044 | Fire-fighting piping | 2025-02-22 | 2025-04-08 | 2025-04-17 | 18700000
PO000775 | PRJ025 | V055 | Electrical cable trays | 2026-03-11 | 2026-04-03 | 2026-04-04 | 17000000
PO000776 | PRJ026 | V006 | Safety harnesses | 2024-12-06 | 2025-01-13 | 2025-01-22 | 3500000
PO000777 | PRJ027 | V017 | Diesel generator hire | 2026-05-04 | 2026-06-04 | 2026-06-07 | 14200000
PO000778 | PRJ028 | V028 | Tower crane hire | 2024-12-28 | 2025-02-05 | 2025-02-12 | 29400000
PO000779 | PRJ029 | V039 | Facade glazing panels | 2025-01-10 | 2025-01-20 | 2025-01-28 | 33100000
PO000780 | PRJ030 | V050 | Waterproofing membrane | 2025-12-08 | 2026-01-09 | 2026-01-11 | 15600000
PO000781 | PRJ001 | V018 | TMT rebar Fe500D | 2025-03-19 | 2025-04-14 | 2025-05-15 | 33200000
PO000782 | PRJ002 | V012 | OPC 53 grade cement | 2024-11-14 | 2024-11-28 | 2024-11-24 | 35600000
PO000783 | PRJ003 | V023 | Ready-mix concrete M35 | 2025-04-04 | 2025-05-16 | 2025-05-23 | 22400000
PO000784 | PRJ004 | V034 | Structural steel sections | 2025-08-03 | 2025-08-26 | 2025-08-29 | 27600000
PO000785 | PRJ005 | V045 | Aluminium formwork | 2025-03-02 | 2025-04-06 | 2025-04-02 | 18700000
PO000786 | PRJ006 | V056 | Fire-fighting piping | 2024-12-10 | 2025-01-04 | 2025-01-04 | 31600000
PO000787 | PRJ007 | V007 | Electrical cable trays | 2025-12-11 | 2025-12-23 | 2025-12-19 | 37000000
PO000788 | PRJ008 | V018 | Safety harnesses | 2024-10-23 | 2024-11-14 | 2024-11-23 | 26300000
PO000789 | PRJ009 | V029 | Diesel generator hire | 2026-05-09 | 2026-06-20 | 2026-06-20 | 31000000
PO000790 | PRJ010 | V040 | Tower crane hire | 2024-12-11 | 2025-01-04 | 2025-01-03 | 4900000
PO000791 | PRJ011 | V025 | Facade glazing panels | 2025-03-02 | 2025-03-14 | 2025-04-08 | 29100000
PO000792 | PRJ012 | V002 | Waterproofing membrane | 2025-10-09 | 2025-11-21 | 2025-11-25 | 34700000
PO000793 | PRJ013 | V013 | TMT rebar Fe500D | 2025-02-25 | 2025-04-08 | 2025-04-15 | 24300000
PO000794 | PRJ014 | V024 | OPC 53 grade cement | 2025-12-04 | 2026-01-10 | 2026-01-15 | 11000000
PO000795 | PRJ015 | V035 | Ready-mix concrete M35 | 2024-10-04 | 2024-11-12 | 2024-11-16 | 1600000
PO000796 | PRJ016 | V046 | Structural steel sections | 2024-12-04 | 2025-01-17 | 2025-01-26 | 28900000
PO000797 | PRJ017 | V057 | Aluminium formwork | 2024-10-11 | 2024-10-25 | 2024-11-01 | 2300000
PO000798 | PRJ018 | V008 | Fire-fighting piping | 2025-04-13 | 2025-05-24 | 2025-05-27 | 15300000
PO000799 | PRJ019 | V019 | Electrical cable trays | 2024-10-07 | 2024-10-20 | 2024-10-20 | 500000
PO000800 | PRJ020 | V030 | Safety harnesses | 2025-08-18 | 2025-09-25 | 2025-09-23 | 20600000

## answer_key
po_id | is_at_risk | risk_reason
PO000001 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000002 | N
PO000003 | N
PO000004 | N
PO000005 | N
PO000006 | N
PO000007 | N
PO000008 | N
PO000009 | N
PO000010 | N
PO000011 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000012 | N
PO000013 | N
PO000014 | N
PO000015 | N
PO000016 | N
PO000017 | N
PO000018 | N
PO000019 | N
PO000020 | N
PO000021 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000022 | N
PO000023 | N
PO000024 | N
PO000025 | N
PO000026 | N
PO000027 | N
PO000028 | N
PO000029 | N
PO000030 | N
PO000031 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000032 | N
PO000033 | N
PO000034 | N
PO000035 | N
PO000036 | N
PO000037 | N
PO000038 | N
PO000039 | N
PO000040 | N
PO000041 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000042 | N
PO000043 | N
PO000044 | N
PO000045 | N
PO000046 | N
PO000047 | N
PO000048 | N
PO000049 | N
PO000050 | N
PO000051 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000052 | N
PO000053 | N
PO000054 | N
PO000055 | N
PO000056 | N
PO000057 | N
PO000058 | N
PO000059 | N
PO000060 | N
PO000061 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000062 | N
PO000063 | N
PO000064 | N
PO000065 | N
PO000066 | N
PO000067 | N
PO000068 | N
PO000069 | N
PO000070 | N
PO000071 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000072 | N
PO000073 | N
PO000074 | N
PO000075 | N
PO000076 | N
PO000077 | N
PO000078 | N
PO000079 | N
PO000080 | N
PO000081 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000082 | N
PO000083 | N
PO000084 | N
PO000085 | N
PO000086 | N
PO000087 | N
PO000088 | N
PO000089 | N
PO000090 | N
PO000091 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000092 | N
PO000093 | N
PO000094 | N
PO000095 | N
PO000096 | N
PO000097 | N
PO000098 | N
PO000099 | N
PO000100 | N
PO000101 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000102 | N
PO000103 | N
PO000104 | N
PO000105 | N
PO000106 | N
PO000107 | N
PO000108 | N
PO000109 | N
PO000110 | N
PO000111 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000112 | N
PO000113 | N
PO000114 | N
PO000115 | N
PO000116 | N
PO000117 | N
PO000118 | N
PO000119 | N
PO000120 | N
PO000121 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000122 | N
PO000123 | N
PO000124 | N
PO000125 | N
PO000126 | N
PO000127 | N
PO000128 | N
PO000129 | N
PO000130 | N
PO000131 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000132 | N
PO000133 | N
PO000134 | N
PO000135 | N
PO000136 | N
PO000137 | N
PO000138 | N
PO000139 | N
PO000140 | N
PO000141 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000142 | N
PO000143 | N
PO000144 | N
PO000145 | N
PO000146 | N
PO000147 | N
PO000148 | N
PO000149 | N
PO000150 | N
PO000151 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000152 | N
PO000153 | N
PO000154 | N
PO000155 | N
PO000156 | N
PO000157 | N
PO000158 | N
PO000159 | N
PO000160 | N
PO000161 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000162 | N
PO000163 | N
PO000164 | N
PO000165 | N
PO000166 | N
PO000167 | N
PO000168 | N
PO000169 | N
PO000170 | N
PO000171 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000172 | N
PO000173 | N
PO000174 | N
PO000175 | N
PO000176 | N
PO000177 | N
PO000178 | N
PO000179 | N
PO000180 | N
PO000181 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000182 | N
PO000183 | N
PO000184 | N
PO000185 | N
PO000186 | N
PO000187 | N
PO000188 | N
PO000189 | N
PO000190 | N
PO000191 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000192 | N
PO000193 | N
PO000194 | N
PO000195 | N
PO000196 | N
PO000197 | N
PO000198 | N
PO000199 | N
PO000200 | N
PO000201 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000202 | N
PO000203 | N
PO000204 | N
PO000205 | N
PO000206 | N
PO000207 | N
PO000208 | N
PO000209 | N
PO000210 | N
PO000211 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000212 | N
PO000213 | N
PO000214 | N
PO000215 | N
PO000216 | N
PO000217 | N
PO000218 | N
PO000219 | N
PO000220 | N
PO000221 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000222 | N
PO000223 | N
PO000224 | N
PO000225 | N
PO000226 | N
PO000227 | N
PO000228 | N
PO000229 | N
PO000230 | N
PO000231 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000232 | N
PO000233 | N
PO000234 | N
PO000235 | N
PO000236 | N
PO000237 | N
PO000238 | N
PO000239 | N
PO000240 | N
PO000241 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000242 | N
PO000243 | N
PO000244 | N
PO000245 | N
PO000246 | N
PO000247 | N
PO000248 | N
PO000249 | N
PO000250 | N
PO000251 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000252 | N
PO000253 | N
PO000254 | N
PO000255 | N
PO000256 | N
PO000257 | N
PO000258 | N
PO000259 | N
PO000260 | N
PO000261 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000262 | N
PO000263 | N
PO000264 | N
PO000265 | N
PO000266 | N
PO000267 | N
PO000268 | N
PO000269 | N
PO000270 | N
PO000271 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000272 | N
PO000273 | N
PO000274 | N
PO000275 | N
PO000276 | N
PO000277 | N
PO000278 | N
PO000279 | N
PO000280 | N
PO000281 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000282 | N
PO000283 | N
PO000284 | N
PO000285 | N
PO000286 | N
PO000287 | N
PO000288 | N
PO000289 | N
PO000290 | N
PO000291 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000292 | N
PO000293 | N
PO000294 | N
PO000295 | N
PO000296 | N
PO000297 | N
PO000298 | N
PO000299 | N
PO000300 | N
PO000301 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000302 | N
PO000303 | N
PO000304 | N
PO000305 | N
PO000306 | N
PO000307 | N
PO000308 | N
PO000309 | N
PO000310 | N
PO000311 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000312 | N
PO000313 | N
PO000314 | N
PO000315 | N
PO000316 | N
PO000317 | N
PO000318 | N
PO000319 | N
PO000320 | N
PO000321 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000322 | N
PO000323 | N
PO000324 | N
PO000325 | N
PO000326 | N
PO000327 | N
PO000328 | N
PO000329 | N
PO000330 | N
PO000331 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000332 | N
PO000333 | N
PO000334 | N
PO000335 | N
PO000336 | N
PO000337 | N
PO000338 | N
PO000339 | N
PO000340 | N
PO000341 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000342 | N
PO000343 | N
PO000344 | N
PO000345 | N
PO000346 | N
PO000347 | N
PO000348 | N
PO000349 | N
PO000350 | N
PO000351 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000352 | N
PO000353 | N
PO000354 | N
PO000355 | N
PO000356 | N
PO000357 | N
PO000358 | N
PO000359 | N
PO000360 | N
PO000361 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000362 | N
PO000363 | N
PO000364 | N
PO000365 | N
PO000366 | N
PO000367 | N
PO000368 | N
PO000369 | N
PO000370 | N
PO000371 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000372 | N
PO000373 | N
PO000374 | N
PO000375 | N
PO000376 | N
PO000377 | N
PO000378 | N
PO000379 | N
PO000380 | N
PO000381 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000382 | N
PO000383 | N
PO000384 | N
PO000385 | N
PO000386 | N
PO000387 | N
PO000388 | N
PO000389 | N
PO000390 | N
PO000391 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000392 | N
PO000393 | N
PO000394 | N
PO000395 | N
PO000396 | N
PO000397 | N
PO000398 | N
PO000399 | N
PO000400 | N
PO000401 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000402 | N
PO000403 | N
PO000404 | N
PO000405 | N
PO000406 | N
PO000407 | N
PO000408 | N
PO000409 | N
PO000410 | N
PO000411 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000412 | N
PO000413 | N
PO000414 | N
PO000415 | N
PO000416 | N
PO000417 | N
PO000418 | N
PO000419 | N
PO000420 | N
PO000421 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000422 | N
PO000423 | N
PO000424 | N
PO000425 | N
PO000426 | N
PO000427 | N
PO000428 | N
PO000429 | N
PO000430 | N
PO000431 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000432 | N
PO000433 | N
PO000434 | N
PO000435 | N
PO000436 | N
PO000437 | N
PO000438 | N
PO000439 | N
PO000440 | N
PO000441 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000442 | N
PO000443 | N
PO000444 | N
PO000445 | N
PO000446 | N
PO000447 | N
PO000448 | N
PO000449 | N
PO000450 | N
PO000451 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000452 | N
PO000453 | N
PO000454 | N
PO000455 | N
PO000456 | N
PO000457 | N
PO000458 | N
PO000459 | N
PO000460 | N
PO000461 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000462 | N
PO000463 | N
PO000464 | N
PO000465 | N
PO000466 | N
PO000467 | N
PO000468 | N
PO000469 | N
PO000470 | N
PO000471 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000472 | N
PO000473 | N
PO000474 | N
PO000475 | N
PO000476 | N
PO000477 | N
PO000478 | N
PO000479 | N
PO000480 | N
PO000481 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000482 | N
PO000483 | N
PO000484 | N
PO000485 | N
PO000486 | N
PO000487 | N
PO000488 | N
PO000489 | N
PO000490 | N
PO000491 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000492 | N
PO000493 | N
PO000494 | N
PO000495 | N
PO000496 | N
PO000497 | N
PO000498 | N
PO000499 | N
PO000500 | N
PO000501 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000502 | N
PO000503 | N
PO000504 | N
PO000505 | N
PO000506 | N
PO000507 | N
PO000508 | N
PO000509 | N
PO000510 | N
PO000511 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000512 | N
PO000513 | N
PO000514 | N
PO000515 | N
PO000516 | N
PO000517 | N
PO000518 | N
PO000519 | N
PO000520 | N
PO000521 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000522 | N
PO000523 | N
PO000524 | N
PO000525 | N
PO000526 | N
PO000527 | N
PO000528 | N
PO000529 | N
PO000530 | N
PO000531 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000532 | N
PO000533 | N
PO000534 | N
PO000535 | N
PO000536 | N
PO000537 | N
PO000538 | N
PO000539 | N
PO000540 | N
PO000541 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000542 | N
PO000543 | N
PO000544 | N
PO000545 | N
PO000546 | N
PO000547 | N
PO000548 | N
PO000549 | N
PO000550 | N
PO000551 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000552 | N
PO000553 | N
PO000554 | N
PO000555 | N
PO000556 | N
PO000557 | N
PO000558 | N
PO000559 | N
PO000560 | N
PO000561 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000562 | N
PO000563 | N
PO000564 | N
PO000565 | N
PO000566 | N
PO000567 | N
PO000568 | N
PO000569 | N
PO000570 | N
PO000571 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000572 | N
PO000573 | N
PO000574 | N
PO000575 | N
PO000576 | N
PO000577 | N
PO000578 | N
PO000579 | N
PO000580 | N
PO000581 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000582 | N
PO000583 | N
PO000584 | N
PO000585 | N
PO000586 | N
PO000587 | N
PO000588 | N
PO000589 | N
PO000590 | N
PO000591 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000592 | N
PO000593 | N
PO000594 | N
PO000595 | N
PO000596 | N
PO000597 | N
PO000598 | N
PO000599 | N
PO000600 | N
PO000601 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000602 | N
PO000603 | N
PO000604 | N
PO000605 | N
PO000606 | N
PO000607 | N
PO000608 | N
PO000609 | N
PO000610 | N
PO000611 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000612 | N
PO000613 | N
PO000614 | N
PO000615 | N
PO000616 | N
PO000617 | N
PO000618 | N
PO000619 | N
PO000620 | N
PO000621 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000622 | N
PO000623 | N
PO000624 | N
PO000625 | N
PO000626 | N
PO000627 | N
PO000628 | N
PO000629 | N
PO000630 | N
PO000631 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000632 | N
PO000633 | N
PO000634 | N
PO000635 | N
PO000636 | N
PO000637 | N
PO000638 | N
PO000639 | N
PO000640 | N
PO000641 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000642 | N
PO000643 | N
PO000644 | N
PO000645 | N
PO000646 | N
PO000647 | N
PO000648 | N
PO000649 | N
PO000650 | N
PO000651 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000652 | N
PO000653 | N
PO000654 | N
PO000655 | N
PO000656 | N
PO000657 | N
PO000658 | N
PO000659 | N
PO000660 | N
PO000661 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000662 | N
PO000663 | N
PO000664 | N
PO000665 | N
PO000666 | N
PO000667 | N
PO000668 | N
PO000669 | N
PO000670 | N
PO000671 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000672 | N
PO000673 | N
PO000674 | N
PO000675 | N
PO000676 | N
PO000677 | N
PO000678 | N
PO000679 | N
PO000680 | N
PO000681 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000682 | N
PO000683 | N
PO000684 | N
PO000685 | N
PO000686 | N
PO000687 | N
PO000688 | N
PO000689 | N
PO000690 | N
PO000691 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000692 | N
PO000693 | N
PO000694 | N
PO000695 | N
PO000696 | N
PO000697 | N
PO000698 | N
PO000699 | N
PO000700 | N
PO000701 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000702 | N
PO000703 | N
PO000704 | N
PO000705 | N
PO000706 | N
PO000707 | N
PO000708 | N
PO000709 | N
PO000710 | N
PO000711 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000712 | N
PO000713 | N
PO000714 | N
PO000715 | N
PO000716 | N
PO000717 | N
PO000718 | N
PO000719 | N
PO000720 | N
PO000721 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000722 | N
PO000723 | N
PO000724 | N
PO000725 | N
PO000726 | N
PO000727 | N
PO000728 | N
PO000729 | N
PO000730 | N
PO000731 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000732 | N
PO000733 | N
PO000734 | N
PO000735 | N
PO000736 | N
PO000737 | N
PO000738 | N
PO000739 | N
PO000740 | N
PO000741 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000742 | N
PO000743 | N
PO000744 | N
PO000745 | N
PO000746 | N
PO000747 | N
PO000748 | N
PO000749 | N
PO000750 | N
PO000751 | Y | Repeat late-delivery pattern for V003; delivery missed promise by more than two weeks.
PO000752 | N
PO000753 | N
PO000754 | N
PO000755 | N
PO000756 | N
PO000757 | N
PO000758 | N
PO000759 | N
PO000760 | N
PO000761 | Y | Repeat late-delivery pattern for V007; delivery missed promise by more than two weeks.
PO000762 | N
PO000763 | N
PO000764 | N
PO000765 | N
PO000766 | N
PO000767 | N
PO000768 | N
PO000769 | N
PO000770 | N
PO000771 | Y | Repeat late-delivery pattern for V012; delivery missed promise by more than two weeks.
PO000772 | N
PO000773 | N
PO000774 | N
PO000775 | N
PO000776 | N
PO000777 | N
PO000778 | N
PO000779 | N
PO000780 | N
PO000781 | Y | Repeat late-delivery pattern for V018; delivery missed promise by more than two weeks.
PO000782 | N
PO000783 | N
PO000784 | N
PO000785 | N
PO000786 | N
PO000787 | N
PO000788 | N
PO000789 | N
PO000790 | N
PO000791 | Y | Repeat late-delivery pattern for V025; delivery missed promise by more than two weeks.
PO000792 | N
PO000793 | N
PO000794 | N
PO000795 | N
PO000796 | N
PO000797 | N
PO000798 | N
PO000799 | N
PO000800 | N

## data_dictionary
sheet_name | column_name | data_type | meaning
dim_vendor | vendor_id | Text | Unique vendor identifier.
dim_vendor | vendor_name | Text | Vendor legal or trading name.
dim_vendor | vendor_category | Text | Primary supply or service category.
dim_vendor | vendor_rating | Rating | Vendor performance rating on a 1–5 scale.
fact_purchase_order | po_id | Text | Unique primary key for the purchase order.
fact_purchase_order | project_id | Text | Project identifier.
fact_purchase_order | vendor_id | Text | Vendor identifier.
fact_purchase_order | item_description | Text | Ordered material, equipment or service.
fact_purchase_order | order_date | Date | Purchase order date.
fact_purchase_order | promised_date | Date | Vendor-promised delivery date.
fact_purchase_order | actual_delivery_date | Date | Actual delivery date.
fact_purchase_order | po_value | Currency (INR) | Purchase order value in INR.
answer_key | po_id | Text | Purchase order primary key.
answer_key | is_at_risk | Text | Y when the purchase order is at risk; otherwise N.
answer_key | risk_reason | Text | Short reason for the risk flag.
data_dictionary | sheet_name | Text | Worksheet containing the documented column.
data_dictionary | column_name | Text | Exact column name used in that worksheet.
data_dictionary | data_type | Text | Expected logical data type and unit.
data_dictionary | meaning | Text | Business meaning of the column.